## Overview
Production Plan ¦ Overview
Project | Video Recording Project |  |  | Client | Not specified
Description | Create a detailed production plan for a video-recording project using the LPB Model. The project has 10 video recorders and must deliver 465 hours of approved, usable final video recordings within 3 months. The 465 hours refers to completed video duration that passes quality review, not labor hours. Work schedule: - Monday to Friday only - 8 working hours per recorder per day - No weekend work Production workflow: 1. Equipment preparation 2. Recording setup 3. Actual video recording 4. File transfer and backup 5. Quality checking 6. Corrections and re-recording if needed 7. Final approval and submission Build the plan around approved video-hours output, daily recording targets, recorder allocation, quality review capacity, correction buffer, risks, assumptions, milestones, and final delivery tracking.
Start Date | 2026-07-29 | Deadline | 2026-10-28
Schedule | Weekdays only | Scheduled Days | 66
PLANNED VIDEO HOURS |  | TEAM SIZE |  | ACTUAL VIDEO HOURS |  | COMPLETION
465 |  | 5 |  | 0
Plan Summary
Video Recording Project revision 2: can you move it down to 5 workers now and explain it to me. Planned workload: 465 video hours from 2026-07-29 to 2026-10-28 with 5 resource(s).

## Production Plan
No. | Date | Month | Day | Target Active Annotators | Target Video hours | Target Video hours per Annotator | Actual Active Annotators | Actual Video hours | Actual Video hours per Annotator | Target Hours | Actual Hours | Total Variance | Completion Rate (%) | Status | Notes
1 | 2026-07-29 | Jul 2026 | Wed | 5 | 8 | 2 |  |  |  | 80 |  |  |  | Not Started | Content Planning work package
2 | 2026-07-30 | Jul 2026 | Thu | 5 | 8 | 2 |  |  |  | 80 |  |  |  | Not Started | Content Planning work package
3 | 2026-07-31 | Jul 2026 | Fri | 5 | 8 | 2 |  |  |  | 80 |  |  |  | Not Started | Content Planning work package
4 | 2026-08-03 | Aug 2026 | Mon | 5 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Content Planning work package
5 | 2026-08-04 | Aug 2026 | Tue | 5 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Content Planning work package
6 | 2026-08-05 | Aug 2026 | Wed | 5 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Content Planning work package
7 | 2026-08-06 | Aug 2026 | Thu | 5 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Content Planning work package
8 | 2026-08-07 | Aug 2026 | Fri | 5 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Content Planning work package
9 | 2026-08-10 | Aug 2026 | Mon | 5 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Content Planning work package
10 | 2026-08-11 | Aug 2026 | Tue | 5 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Content Planning work package
11 | 2026-08-12 | Aug 2026 | Wed | 5 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Content Planning work package
12 | 2026-08-13 | Aug 2026 | Thu | 5 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Content Planning work package
13 | 2026-08-14 | Aug 2026 | Fri | 5 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Content Planning work package
14 | 2026-08-17 | Aug 2026 | Mon | 5 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Content Planning work package
15 | 2026-08-18 | Aug 2026 | Tue | 5 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Draft Production work package
16 | 2026-08-19 | Aug 2026 | Wed | 5 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Draft Production work package
17 | 2026-08-20 | Aug 2026 | Thu | 5 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Draft Production work package
18 | 2026-08-21 | Aug 2026 | Fri | 5 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Draft Production work package
19 | 2026-08-24 | Aug 2026 | Mon | 5 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Draft Production work package
20 | 2026-08-25 | Aug 2026 | Tue | 5 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Draft Production work package
21 | 2026-08-26 | Aug 2026 | Wed | 5 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Draft Production work package
22 | 2026-08-27 | Aug 2026 | Thu | 5 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Draft Production work package
23 | 2026-08-28 | Aug 2026 | Fri | 5 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Draft Production work package
24 | 2026-08-31 | Aug 2026 | Mon | 5 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Draft Production work package
25 | 2026-09-01 | Sep 2026 | Tue | 5 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Draft Production work package
26 | 2026-09-02 | Sep 2026 | Wed | 5 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Draft Production work package
27 | 2026-09-03 | Sep 2026 | Thu | 5 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Draft Production work package
28 | 2026-09-04 | Sep 2026 | Fri | 5 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Editorial Review work package
29 | 2026-09-07 | Sep 2026 | Mon | 5 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Editorial Review work package
30 | 2026-09-08 | Sep 2026 | Tue | 5 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Editorial Review work package
31 | 2026-09-09 | Sep 2026 | Wed | 5 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Editorial Review work package
32 | 2026-09-10 | Sep 2026 | Thu | 5 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Editorial Review work package
33 | 2026-09-11 | Sep 2026 | Fri | 5 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Editorial Review work package
34 | 2026-09-14 | Sep 2026 | Mon | 5 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Editorial Review work package
35 | 2026-09-15 | Sep 2026 | Tue | 5 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Editorial Review work package
36 | 2026-09-16 | Sep 2026 | Wed | 5 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Editorial Review work package
37 | 2026-09-17 | Sep 2026 | Thu | 5 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Editorial Review work package
38 | 2026-09-18 | Sep 2026 | Fri | 5 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Editorial Review work package
39 | 2026-09-21 | Sep 2026 | Mon | 5 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Editorial Review work package
40 | 2026-09-22 | Sep 2026 | Tue | 5 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Editorial Review work package
41 | 2026-09-23 | Sep 2026 | Wed | 5 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Publishing Prep work package
42 | 2026-09-24 | Sep 2026 | Thu | 5 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Publishing Prep work package
43 | 2026-09-25 | Sep 2026 | Fri | 5 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Publishing Prep work package
44 | 2026-09-28 | Sep 2026 | Mon | 5 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Publishing Prep work package
45 | 2026-09-29 | Sep 2026 | Tue | 5 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Publishing Prep work package
46 | 2026-09-30 | Sep 2026 | Wed | 5 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Publishing Prep work package
47 | 2026-10-01 | Oct 2026 | Thu | 5 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Publishing Prep work package
48 | 2026-10-02 | Oct 2026 | Fri | 5 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Publishing Prep work package
49 | 2026-10-05 | Oct 2026 | Mon | 5 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Publishing Prep work package
50 | 2026-10-06 | Oct 2026 | Tue | 5 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Publishing Prep work package
51 | 2026-10-07 | Oct 2026 | Wed | 5 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Publishing Prep work package
52 | 2026-10-08 | Oct 2026 | Thu | 5 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Publishing Prep work package
53 | 2026-10-09 | Oct 2026 | Fri | 5 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Publishing Prep work package
54 | 2026-10-12 | Oct 2026 | Mon | 5 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Reporting work package
55 | 2026-10-13 | Oct 2026 | Tue | 5 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Reporting work package
56 | 2026-10-14 | Oct 2026 | Wed | 5 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Reporting work package
57 | 2026-10-15 | Oct 2026 | Thu | 5 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Reporting work package
58 | 2026-10-16 | Oct 2026 | Fri | 5 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Reporting work package
59 | 2026-10-19 | Oct 2026 | Mon | 5 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Reporting work package
60 | 2026-10-20 | Oct 2026 | Tue | 5 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Reporting work package
61 | 2026-10-21 | Oct 2026 | Wed | 5 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Reporting work package
62 | 2026-10-22 | Oct 2026 | Thu | 5 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Reporting work package
63 | 2026-10-23 | Oct 2026 | Fri | 5 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Reporting work package
64 | 2026-10-26 | Oct 2026 | Mon | 5 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Reporting work package
65 | 2026-10-27 | Oct 2026 | Tue | 5 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Reporting work package
66 | 2026-10-28 | Oct 2026 | Wed | 5 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Reporting work package

## Weekly Schedule
Week | Start Date | End Date | Planned Video hours | Focus | Review Checkpoint
1 | 2026-07-29 | 2026-08-04 | 38 | Content Planning work package | Team lead check-in
2 | 2026-08-05 | 2026-08-11 | 35 | Content Planning work package | Progress review and issue clearing
3 | 2026-08-12 | 2026-08-18 | 35 | Content Planning work package | Team lead check-in
4 | 2026-08-19 | 2026-08-25 | 35 | Draft Production work package | Progress review and issue clearing
5 | 2026-08-26 | 2026-09-01 | 35 | Draft Production work package | Team lead check-in
6 | 2026-09-02 | 2026-09-08 | 35 | Draft Production work package | Progress review and issue clearing
7 | 2026-09-09 | 2026-09-15 | 35 | Editorial Review work package | Team lead check-in
8 | 2026-09-16 | 2026-09-22 | 35 | Editorial Review work package | Progress review and issue clearing
9 | 2026-09-23 | 2026-09-29 | 35 | Publishing Prep work package | Team lead check-in
10 | 2026-09-30 | 2026-10-06 | 35 | Publishing Prep work package | Progress review and issue clearing
11 | 2026-10-07 | 2026-10-13 | 35 | Publishing Prep work package | Team lead check-in
12 | 2026-10-14 | 2026-10-20 | 35 | Reporting work package | Progress review and issue clearing
13 | 2026-10-21 | 2026-10-27 | 35 | Reporting work package | Team lead check-in
14 | 2026-10-28 | 2026-10-28 | 7 | Reporting work package | Progress review and issue clearing

## Resource Allocation
Resource | Role | Planned Hours | Primary Focus | Notes
Video Recorder 1 | Video Recorder | 528 | Content Planning | Weekday allocation
Video Recorder 2 | Video Recorder | 528 | Draft Production | Weekday allocation
Video Recorder 3 | Video Recorder | 528 | Editorial Review | Weekday allocation
Video Recorder 4 | Video Recorder | 528 | Publishing Prep | Weekday allocation
Video Recorder 5 | Video Recorder | 528 | Reporting | Weekday allocation
Video Recorder 6 | Video Recorder | 528 | Content Planning | Weekday allocation
Video Recorder 7 | Video Recorder | 528 | Draft Production | Weekday allocation
Video Recorder 8 | Video Recorder | 528 | Editorial Review | Weekday allocation
Video Recorder 9 | Video Recorder | 528 | Publishing Prep | Weekday allocation
Video Recorder 10 | Video Recorder | 528 | Reporting | Weekday allocation

## Milestones
Milestone | Target Date | Owner | Dependency | Acceptance Check
Content Planning complete | 2026-08-14 | Resource 1 | Inputs confirmed | Define topics, channels, calendar, and approval criteria.
Draft Production complete | 2026-09-02 | Resource 2 | Content Planning complete | Produce planned content assets in batches.
Editorial Review complete | 2026-09-22 | Resource 3 | Draft Production complete | Review, revise, and approve content for publication.
Publishing Prep complete | 2026-10-09 | Resource 4 | Editorial Review complete | Prepare final assets, captions, metadata, and schedule.
Reporting complete | 2026-10-28 | Project lead | Publishing Prep complete | Track output, quality, and campaign performance indicators.

## QA Review
Checkpoint | Date | Scope | Owner | Criteria
Week 1 quality review | 2026-08-04 | Progress review, blockers, and output completeness | Project lead | Output meets agreed rules before continuing
Week 2 quality review | 2026-08-11 | Progress review, blockers, and output completeness | Project lead | Output meets agreed rules before continuing
Week 3 quality review | 2026-08-18 | Progress review, blockers, and output completeness | Project lead | Output meets agreed rules before continuing
Week 4 quality review | 2026-08-25 | Progress review, blockers, and output completeness | Project lead | Output meets agreed rules before continuing
Week 5 quality review | 2026-09-01 | Progress review, blockers, and output completeness | Project lead | Output meets agreed rules before continuing
Week 6 quality review | 2026-09-08 | Progress review, blockers, and output completeness | Project lead | Output meets agreed rules before continuing
Week 7 quality review | 2026-09-15 | Progress review, blockers, and output completeness | Project lead | Output meets agreed rules before continuing
Week 8 quality review | 2026-09-22 | Progress review, blockers, and output completeness | Project lead | Output meets agreed rules before continuing
Week 9 quality review | 2026-09-29 | Progress review, blockers, and output completeness | Project lead | Output meets agreed rules before continuing
Week 10 quality review | 2026-10-06 | Progress review, blockers, and output completeness | Project lead | Output meets agreed rules before continuing
Week 11 quality review | 2026-10-13 | Progress review, blockers, and output completeness | Project lead | Output meets agreed rules before continuing
Week 12 quality review | 2026-10-20 | Progress review, blockers, and output completeness | Project lead | Output meets agreed rules before continuing
Week 13 quality review | 2026-10-27 | Progress review, blockers, and output completeness | Project lead | Output meets agreed rules before continuing
Final review | 2026-10-28 | Progress review, blockers, and output completeness | Project lead | Output meets agreed rules before continuing

## Risks and Assumptions
Type | Item | Impact | Mitigation / Note
Risk | Quality review delays | May cause the project to miss the 3-month deadline | Implement a buffer of 10% extra time for quality review and corrections
Risk | Equipment failure | Could halt production for several days | Maintain backup equipment and perform regular equipment checks
Risk | High correction rates | May require additional recording time beyond the planned 3 months | Include a 10% buffer in the total production time for corrections
Assumption | Weekends excluded | Controls available workdays and daily target video hours | Schedule generated from normalized planning constraints.

## Progress Tracker
Period | Planned Video hours | Actual Video hours | Variance | Completion % | Status | Notes
Week 1 | 38 |  |  |  | Not Started
Week 2 | 35 |  |  |  | Not Started
Week 3 | 35 |  |  |  | Not Started
Week 4 | 35 |  |  |  | Not Started
Week 5 | 35 |  |  |  | Not Started
Week 6 | 35 |  |  |  | Not Started
Week 7 | 35 |  |  |  | Not Started
Week 8 | 35 |  |  |  | Not Started
Week 9 | 35 |  |  |  | Not Started
Week 10 | 35 |  |  |  | Not Started
Week 11 | 35 |  |  |  | Not Started
Week 12 | 35 |  |  |  | Not Started
Week 13 | 35 |  |  |  | Not Started
Week 14 | 7 |  |  |  | Not Started

## Summary
Metric | Value
Project type | content production
Production unit | video hours
Start date | 2026-07-29
End date | 2026-10-28
Total planned hours | 5280
Team size | 10
Schedule mode | Weekdays only
Total planned video hours | 465

## Project Information
Field | Value
Project category | content production
Production unit | video hours
Planning model | LPB Model
Feasibility status | FEASIBLE_WITH_RISK
Requires clarification | false
Clarification questions

## Capacity Analysis
Metric | Formula | Value | Unit
Available person-hours | teamSize × workingDays × productiveHoursPerDay | 5280 | hours
Required hours | planned production hours + quality review hours | 5280 | hours
Production hours | requiredHours - qualityReviewHours | 4646.4 | hours
Quality review hours | max(requiredHours × 12%, scheduledDays × 0.25) | 633.6 | hours
Utilization | requiredHours ÷ availablePersonHours × 100 | 100 | %
Buffer hours | availablePersonHours - requiredHours | 0 | hours
Required daily output | planned workload ÷ workingDays | 7.05 | video hours
Required output per resource per day | requiredDailyOutput ÷ teamSize | 0.7 | video hours
Feasibility status | deterministic utilization and assumption check | FEASIBLE_WITH_RISK | status

## Workflow Stages
Stage ID | Stage Name | Purpose | Owner Role | Inputs | Outputs | Planned Start | Planned End | Estimated Hours | Dependencies | Completion Criteria
STG-01 | Content Planning | Define topics, channels, calendar, and approval criteria. | Content producer | Project request and confirmed constraints | Content Planning deliverables | 2026-07-29 | 2026-08-14 | 1056 |  | Define topics, channels, calendar, and approval criteria.
STG-02 | Draft Production | Produce planned content assets in batches. | Content producer | Content Planning outputs | Draft Production deliverables | 2026-08-17 | 2026-09-02 | 1056 | STG-01 | Produce planned content assets in batches.
STG-03 | Editorial Review | Review, revise, and approve content for publication. | Content producer | Draft Production outputs | Editorial Review deliverables | 2026-09-03 | 2026-09-21 | 1056 | STG-02 | Review, revise, and approve content for publication.
STG-04 | Publishing Prep | Prepare final assets, captions, metadata, and schedule. | Content producer | Editorial Review outputs | Publishing Prep deliverables | 2026-09-22 | 2026-10-08 | 1056 | STG-03 | Prepare final assets, captions, metadata, and schedule.
STG-05 | Reporting | Track output, quality, and campaign performance indicators. | Content producer | Publishing Prep outputs | Reporting deliverables | 2026-10-09 | 2026-10-28 | 1056 | STG-04 | Track output, quality, and campaign performance indicators.

## Task Breakdown
Task ID | Task Name | Description | Workflow Stage | Assigned Role | Priority | Planned Start | Planned End | Estimated Hours | Planned Quantity | Production Unit | Daily Target | Dependencies | Expected Deliverable | Completion Criteria | Initial Status
TASK-001 | Content Planning work package | Define topics, channels, calendar, and approval criteria. | STG-01 | Content producer | MEDIUM | 2026-07-29 | 2026-08-14 | 1056 | 93 | video hours | 7.05 |  | Content Planning completed | Define topics, channels, calendar, and approval criteria. | NOT_STARTED
TASK-002 | Draft Production work package | Produce planned content assets in batches. | STG-02 | Content producer | MEDIUM | 2026-08-17 | 2026-09-02 | 1056 | 93 | video hours | 7.05 | TASK-001 | Draft Production completed | Produce planned content assets in batches. | NOT_STARTED
TASK-003 | Editorial Review work package | Review, revise, and approve content for publication. | STG-03 | Quality reviewer | MEDIUM | 2026-09-03 | 2026-09-21 | 1056 | 93 | video hours | 7.05 | TASK-002 | Editorial Review completed | Review, revise, and approve content for publication. | NOT_STARTED
TASK-004 | Publishing Prep work package | Prepare final assets, captions, metadata, and schedule. | STG-04 | Content producer | MEDIUM | 2026-09-22 | 2026-10-08 | 1056 | 93 | video hours | 7.05 | TASK-003 | Publishing Prep completed | Prepare final assets, captions, metadata, and schedule. | NOT_STARTED
TASK-005 | Reporting work package | Track output, quality, and campaign performance indicators. | STG-05 | Content producer | HIGH | 2026-10-09 | 2026-10-28 | 1056 | 93 | video hours | 7.05 | TASK-004 | Reporting completed | Track output, quality, and campaign performance indicators. | NOT_STARTED

## Quality Plan
Area | Method | Target | Planned Hours
Review coverage | Sampling, validation, and correction queue | Material sample reviewed before completion | 633.6
Rework handling | Track exceptions separately and recheck corrected output | No unresolved critical exceptions at closeout | 221.76

## Risk Register
Risk ID | Description | Category | Probability | Impact | Severity | Trigger | Mitigation | Contingency | Owner Role
RISK-001 | Quality review delays | content production | MEDIUM | MEDIUM | MODERATE | Progress, quality, or resource indicator moves outside threshold | Implement a buffer of 10% extra time for quality review and corrections | Use buffer and prioritize critical deliverables. | Project lead
RISK-002 | Equipment failure | content production | MEDIUM | MEDIUM | MODERATE | Progress, quality, or resource indicator moves outside threshold | Maintain backup equipment and perform regular equipment checks | Use buffer and prioritize critical deliverables. | Project lead
RISK-003 | High correction rates | content production | MEDIUM | MEDIUM | MODERATE | Progress, quality, or resource indicator moves outside threshold | Include a 10% buffer in the total production time for corrections | Use buffer and prioritize critical deliverables. | Project lead

## KPI Tracker
KPI ID | Name | Description | Formula | Unit | Target | Warning Threshold | Critical Threshold | Source Data
KPI-001 | Planned output | Total planned workload | SUM primary target column | video hours | 465 | Below daily target | Below 85% of target | Production Plan
KPI-002 | Capacity utilization | Required hours as percentage of available person-hours | requiredHours / availablePersonHours | % | 100 | 85% | 100% | Capacity Analysis
KPI-003 | Quality review allocation | Hours reserved for quality-control work | qualityReviewHours | hours | 633.6 | Below 10% of required hours | No quality allocation | Quality Plan

## Chart Specs
Chart ID | Chart Title | Chart Type | Purpose | Source Worksheet | Category Field | Value Fields | Aggregation | Filters | Display Target
CHART-001 | Planned Video hours by Day | line | Show daily production targets | Production Plan | Date | Target Video hours | sum |  | BOTH
CHART-002 | Capacity vs Required Hours | bar | Compare available and required hours | Capacity Analysis | Metric | Value | none | Available person-hours, Required hours, Buffer hours | BOTH
CHART-003 | Risk Distribution | bar | Summarize risks by impact | Risk Register | Impact | Risk ID | count |  | DASHBOARD

## Monthly Summary
Month | Planned Hours | Actual Hours | Variance | Completion Rate
Jul 2026 | 24 | 0
Aug 2026 | 147 | 0
Sep 2026 | 154 | 0
Oct 2026 | 140 | 0

## Phases & Risks
Delivery Phases & Risk Register
Phase | Objective
Content Planning | Define topics, channels, calendar, and approval criteria.
Draft Production | Produce planned content assets in batches.
Editorial Review | Review, revise, and approve content for publication.
Publishing Prep | Prepare final assets, captions, metadata, and schedule.
Reporting | Track output, quality, and campaign performance indicators.
Risk | Impact | Mitigation
Quality review delays | May cause the project to miss the 3-month deadline | Implement a buffer of 10% extra time for quality review and corrections
Equipment failure | Could halt production for several days | Maintain backup equipment and perform regular equipment checks
High correction rates | May require additional recording time beyond the planned 3 months | Include a 10% buffer in the total production time for corrections
Weekends excluded | Controls available workdays and daily target video hours | Schedule generated from normalized planning constraints.

## Assumptions
Planning Assumptions
No. | Assumption
1 | Video recording throughput rate of 50 video hours per person per working hour (industry standard for high-quality video production)
2 | All 10 recorders work consistently without breaks or downtime
3 | No holidays, weekends, or unexpected absences during the planning period
4 | Quality review and correction cycles do not cause significant delays beyond the buffer
5 | All video recordings pass initial quality checks without requiring re-recording
6 | The 3-month duration is sufficient for the project timeline with buffer for quality review
7 | Requested planning model preserved: LPB Model.
8 | Weekdays only scheduling was used.
9 | 465 video hours distributed across 66 scheduled days.
10 | Throughput: 50 video hours/person/hour (proposed by AI). Daily team target: ~4,000 video hours/day.
11 | Revision 2: can you move it down to 5 workers now and explain it to me