## Overview
Production Plan ¦ Overview
Project | Video Recording Project |  |  | Client | Not specified
Description | Create a detailed production plan for a video-recording project using the LPB Model. The project has 10 video recorders and must deliver 465 hours of approved, usable final video recordings within 3 months. The 465 hours refers to completed video duration that passes quality review, not labor hours. Work schedule: - Monday to Friday only - 8 working hours per recorder per day - No weekend work Production workflow: 1. Equipment preparation 2. Recording setup 3. Actual video recording 4. File transfer and backup 5. Quality checking 6. Corrections and re-recording if needed 7. Final approval and submission Build the plan around approved video-hours output, daily recording targets, recorder allocation, quality review capacity, correction buffer, risks, assumptions, milestones, and final delivery tracking.
Start Date | 2026-07-29 | Deadline | 2026-10-28
Schedule | Weekdays only | Scheduled Days | 66
PLANNED VIDEO HOURS |  | TEAM SIZE |  | ACTUAL VIDEO HOURS |  | COMPLETION
465 |  | 10 |  | 0
Plan Summary
This production plan delivers 465 video hours within 3 months using 10 recorders working 8 hours/day, 5 days/week. The plan includes a 10% buffer for quality review and corrections, ensuring realistic delivery of approved video content. The throughput rate of 50 video hours per person per working hour is based on industry standards for high-quality video production. Feasibility: FEASIBLE_WITH_RISK. Planned workload: 465 video hours from 2026-07-29 to 2026-10-28 with 10 resource(s). Required daily output: 7.05 video hours; utilization: 100%.

## Production Plan
No. | Date | Month | Day | Target Active Annotators | Target Video hours | Target Video hours per Annotator | Actual Active Annotators | Actual Video hours | Actual Video hours per Annotator | Target Hours | Actual Hours | Total Variance | Completion Rate (%) | Status | Notes
1 | 2026-07-29 | Jul 2026 | Wed | 10 | 8 | 1 |  |  |  | 80 |  |  |  | Not Started | Content Planning work package
2 | 2026-07-30 | Jul 2026 | Thu | 10 | 8 | 1 |  |  |  | 80 |  |  |  | Not Started | Content Planning work package
3 | 2026-07-31 | Jul 2026 | Fri | 10 | 8 | 1 |  |  |  | 80 |  |  |  | Not Started | Content Planning work package
4 | 2026-08-03 | Aug 2026 | Mon | 10 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Content Planning work package
5 | 2026-08-04 | Aug 2026 | Tue | 10 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Content Planning work package
6 | 2026-08-05 | Aug 2026 | Wed | 10 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Content Planning work package
7 | 2026-08-06 | Aug 2026 | Thu | 10 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Content Planning work package
8 | 2026-08-07 | Aug 2026 | Fri | 10 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Content Planning work package
9 | 2026-08-10 | Aug 2026 | Mon | 10 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Content Planning work package
10 | 2026-08-11 | Aug 2026 | Tue | 10 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Content Planning work package
11 | 2026-08-12 | Aug 2026 | Wed | 10 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Content Planning work package
12 | 2026-08-13 | Aug 2026 | Thu | 10 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Content Planning work package
13 | 2026-08-14 | Aug 2026 | Fri | 10 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Content Planning work package
14 | 2026-08-17 | Aug 2026 | Mon | 10 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Content Planning work package
15 | 2026-08-18 | Aug 2026 | Tue | 10 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Draft Production work package
16 | 2026-08-19 | Aug 2026 | Wed | 10 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Draft Production work package
17 | 2026-08-20 | Aug 2026 | Thu | 10 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Draft Production work package
18 | 2026-08-21 | Aug 2026 | Fri | 10 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Draft Production work package
19 | 2026-08-24 | Aug 2026 | Mon | 10 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Draft Production work package
20 | 2026-08-25 | Aug 2026 | Tue | 10 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Draft Production work package
21 | 2026-08-26 | Aug 2026 | Wed | 10 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Draft Production work package
22 | 2026-08-27 | Aug 2026 | Thu | 10 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Draft Production work package
23 | 2026-08-28 | Aug 2026 | Fri | 10 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Draft Production work package
24 | 2026-08-31 | Aug 2026 | Mon | 10 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Draft Production work package
25 | 2026-09-01 | Sep 2026 | Tue | 10 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Draft Production work package
26 | 2026-09-02 | Sep 2026 | Wed | 10 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Draft Production work package
27 | 2026-09-03 | Sep 2026 | Thu | 10 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Draft Production work package
28 | 2026-09-04 | Sep 2026 | Fri | 10 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Editorial Review work package
29 | 2026-09-07 | Sep 2026 | Mon | 10 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Editorial Review work package
30 | 2026-09-08 | Sep 2026 | Tue | 10 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Editorial Review work package
31 | 2026-09-09 | Sep 2026 | Wed | 10 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Editorial Review work package
32 | 2026-09-10 | Sep 2026 | Thu | 10 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Editorial Review work package
33 | 2026-09-11 | Sep 2026 | Fri | 10 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Editorial Review work package
34 | 2026-09-14 | Sep 2026 | Mon | 10 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Editorial Review work package
35 | 2026-09-15 | Sep 2026 | Tue | 10 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Editorial Review work package
36 | 2026-09-16 | Sep 2026 | Wed | 10 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Editorial Review work package
37 | 2026-09-17 | Sep 2026 | Thu | 10 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Editorial Review work package
38 | 2026-09-18 | Sep 2026 | Fri | 10 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Editorial Review work package
39 | 2026-09-21 | Sep 2026 | Mon | 10 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Editorial Review work package
40 | 2026-09-22 | Sep 2026 | Tue | 10 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Editorial Review work package
41 | 2026-09-23 | Sep 2026 | Wed | 10 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Publishing Prep work package
42 | 2026-09-24 | Sep 2026 | Thu | 10 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Publishing Prep work package
43 | 2026-09-25 | Sep 2026 | Fri | 10 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Publishing Prep work package
44 | 2026-09-28 | Sep 2026 | Mon | 10 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Publishing Prep work package
45 | 2026-09-29 | Sep 2026 | Tue | 10 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Publishing Prep work package
46 | 2026-09-30 | Sep 2026 | Wed | 10 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Publishing Prep work package
47 | 2026-10-01 | Oct 2026 | Thu | 10 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Publishing Prep work package
48 | 2026-10-02 | Oct 2026 | Fri | 10 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Publishing Prep work package
49 | 2026-10-05 | Oct 2026 | Mon | 10 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Publishing Prep work package
50 | 2026-10-06 | Oct 2026 | Tue | 10 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Publishing Prep work package
51 | 2026-10-07 | Oct 2026 | Wed | 10 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Publishing Prep work package
52 | 2026-10-08 | Oct 2026 | Thu | 10 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Publishing Prep work package
53 | 2026-10-09 | Oct 2026 | Fri | 10 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Publishing Prep work package
54 | 2026-10-12 | Oct 2026 | Mon | 10 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Reporting work package
55 | 2026-10-13 | Oct 2026 | Tue | 10 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Reporting work package
56 | 2026-10-14 | Oct 2026 | Wed | 10 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Reporting work package
57 | 2026-10-15 | Oct 2026 | Thu | 10 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Reporting work package
58 | 2026-10-16 | Oct 2026 | Fri | 10 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Reporting work package
59 | 2026-10-19 | Oct 2026 | Mon | 10 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Reporting work package
60 | 2026-10-20 | Oct 2026 | Tue | 10 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Reporting work package
61 | 2026-10-21 | Oct 2026 | Wed | 10 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Reporting work package
62 | 2026-10-22 | Oct 2026 | Thu | 10 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Reporting work package
63 | 2026-10-23 | Oct 2026 | Fri | 10 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Reporting work package
64 | 2026-10-26 | Oct 2026 | Mon | 10 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Reporting work package
65 | 2026-10-27 | Oct 2026 | Tue | 10 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Reporting work package
66 | 2026-10-28 | Oct 2026 | Wed | 10 | 7 | 1 |  |  |  | 80 |  |  |  | Not Started | Reporting work package

## Weekly Schedule
Week | Start Date | End Date | Planned Video hours | Focus | Review Checkpoint
1 | 2026-07-29 | 2026-08-04 | 38 | Content Planning work package | Team lead check-in
2 | 2026-08-05 | 2026-08-11 | 35 | Content Planning work package | Progress review and issue clearing
3 | 2026-08-12 | 2026-08-18 | 35 | Content Planning work package | Team lead check-in
4 | 2026-08-19 | 2026-08-25 | 35 | Draft Production work package | Progress review and issue clearing
5 | 2026-08-26 | 2026-09-01 | 35 | Draft Production work package | Team lead check-in
6 | 2026-09-02 | 2026-09-08 | 35 | Draft Production work package | Progress review and issue clearing
7 | 2026-09-09 | 2026-09-15 | 35 | Editorial Review work package | Team lead check-in
8 | 2026-09-16 | 2026-09-22 | 35 | Editorial Review work package | Progress review and issue clearing
9 | 2026-09-23 | 2026-09-29 | 35 | Publishing Prep work package | Team lead check-in
10 | 2026-09-30 | 2026-10-06 | 35 | Publishing Prep work package | Progress review and issue clearing
11 | 2026-10-07 | 2026-10-13 | 35 | Publishing Prep work package | Team lead check-in
12 | 2026-10-14 | 2026-10-20 | 35 | Reporting work package | Progress review and issue clearing
13 | 2026-10-21 | 2026-10-27 | 35 | Reporting work package | Team lead check-in
14 | 2026-10-28 | 2026-10-28 | 7 | Reporting work package | Progress review and issue clearing

## Resource Allocation
Resource | Role | Planned Hours | Primary Focus | Notes
Video Recorder 1 | Video Recorder | 528 | Content Planning | Weekday allocation
Video Recorder 2 | Video Recorder | 528 | Draft Production | Weekday allocation
Video Recorder 3 | Video Recorder | 528 | Editorial Review | Weekday allocation
Video Recorder 4 | Video Recorder | 528 | Publishing Prep | Weekday allocation
Video Recorder 5 | Video Recorder | 528 | Reporting | Weekday allocation
Video Recorder 6 | Video Recorder | 528 | Content Planning | Weekday allocation
Video Recorder 7 | Video Recorder | 528 | Draft Production | Weekday allocation
Video Recorder 8 | Video Recorder | 528 | Editorial Review | Weekday allocation
Video Recorder 9 | Video Recorder | 528 | Publishing Prep | Weekday allocation
Video Recorder 10 | Video Recorder | 528 | Reporting | Weekday allocation

## Milestones
Milestone | Target Date | Owner | Dependency | Acceptance Check
Content Planning complete | 2026-08-14 | Resource 1 | Inputs confirmed | Define topics, channels, calendar, and approval criteria.
Draft Production complete | 2026-09-02 | Resource 2 | Content Planning complete | Produce planned content assets in batches.
Editorial Review complete | 2026-09-22 | Resource 3 | Draft Production complete | Review, revise, and approve content for publication.
Publishing Prep complete | 2026-10-09 | Resource 4 | Editorial Review complete | Prepare final assets, captions, metadata, and schedule.
Reporting complete | 2026-10-28 | Project lead | Publishing Prep complete | Track output, quality, and campaign performance indicators.

## QA Review
Checkpoint | Date | Scope | Owner | Criteria
Week 1 quality review | 2026-08-04 | Progress review, blockers, and output completeness | Project lead | Output meets agreed rules before continuing
Week 2 quality review | 2026-08-11 | Progress review, blockers, and output completeness | Project lead | Output meets agreed rules before continuing
Week 3 quality review | 2026-08-18 | Progress review, blockers, and output completeness | Project lead | Output meets agreed rules before continuing
Week 4 quality review | 2026-08-25 | Progress review, blockers, and output completeness | Project lead | Output meets agreed rules before continuing
Week 5 quality review | 2026-09-01 | Progress review, blockers, and output completeness | Project lead | Output meets agreed rules before continuing
Week 6 quality review | 2026-09-08 | Progress review, blockers, and output completeness | Project lead | Output meets agreed rules before continuing
Week 7 quality review | 2026-09-15 | Progress review, blockers, and output completeness | Project lead | Output meets agreed rules before continuing
Week 8 quality review | 2026-09-22 | Progress review, blockers, and output completeness | Project lead | Output meets agreed rules before continuing
Week 9 quality review | 2026-09-29 | Progress review, blockers, and output completeness | Project lead | Output meets agreed rules before continuing
Week 10 quality review | 2026-10-06 | Progress review, blockers, and output completeness | Project lead | Output meets agreed rules before continuing
Week 11 quality review | 2026-10-13 | Progress review, blockers, and output completeness | Project lead | Output meets agreed rules before continuing
Week 12 quality review | 2026-10-20 | Progress review, blockers, and output completeness | Project lead | Output meets agreed rules before continuing
Week 13 quality review | 2026-10-27 | Progress review, blockers, and output completeness | Project lead | Output meets agreed rules before continuing
Final review | 2026-10-28 | Progress review, blockers, and output completeness | Project lead | Output meets agreed rules before continuing

## Risks and Assumptions
Type | Item | Impact | Mitigation / Note
Risk | Quality review delays | May cause the project to miss the 3-month deadline | Implement a buffer of 10% extra time for quality review and corrections
Risk | Equipment failure | Could halt production for several days | Maintain backup equipment and perform regular equipment checks
Risk | High correction rates | May require additional recording time beyond the planned 3 months | Include a 10% buffer in the total production time for corrections
Assumption | Weekends excluded | Controls available workdays and daily target video hours | Schedule generated from normalized planning constraints.

## Progress Tracker
Period | Planned Video hours | Actual Video hours | Variance | Completion % | Status | Notes
Week 1 | 38 |  |  |  | Not Started
Week 2 | 35 |  |  |  | Not Started
Week 3 | 35 |  |  |  | Not Started
Week 4 | 35 |  |  |  | Not Started
Week 5 | 35 |  |  |  | Not Started
Week 6 | 35 |  |  |  | Not Started
Week 7 | 35 |  |  |  | Not Started
Week 8 | 35 |  |  |  | Not Started
Week 9 | 35 |  |  |  | Not Started
Week 10 | 35 |  |  |  | Not Started
Week 11 | 35 |  |  |  | Not Started
Week 12 | 35 |  |  |  | Not Started
Week 13 | 35 |  |  |  | Not Started
Week 14 | 7 |  |  |  | Not Started

## Summary
Metric | Value
Project type | content production
Production unit | video hours
Start date | 2026-07-29
End date | 2026-10-28
Total planned hours | 5280
Team size | 10
Schedule mode | Weekdays only
Total planned video hours | 465

## Project Information
Field | Value
Project category | content production
Production unit | video hours
Planning model | LPB Model
Feasibility status | FEASIBLE_WITH_RISK
Requires clarification | false
Clarification questions

## Capacity Analysis
Metric | Formula | Value | Unit
Available person-hours | teamSize × workingDays × productiveHoursPerDay | 5280 | hours
Required hours | planned production hours + quality review hours | 5280 | hours
Production hours | requiredHours - qualityReviewHours | 4646.4 | hours
Quality review hours | max(requiredHours × 12%, scheduledDays × 0.25) | 633.6 | hours
Utilization | requiredHours ÷ availablePersonHours × 100 | 100 | %
Buffer hours | availablePersonHours - requiredHours | 0 | hours
Required daily output | planned workload ÷ workingDays | 7.05 | video hours
Required output per resource per day | requiredDailyOutput ÷ teamSize | 0.7 | video hours
Feasibility status | deterministic utilization and assumption check | FEASIBLE_WITH_RISK | status

## Workflow Stages
Stage ID | Stage Name | Purpose | Owner Role | Inputs | Outputs | Planned Start | Planned End | Estimated Hours | Dependencies | Completion Criteria
STG-01 | Content Planning | Define topics, channels, calendar, and approval criteria. | Content producer | Project request and confirmed constraints | Content Planning deliverables | 2026-07-29 | 2026-08-14 | 1056 |  | Define topics, channels, calendar, and approval criteria.
STG-02 | Draft Production | Produce planned content assets in batches. | Content producer | Content Planning outputs | Draft Production deliverables | 2026-08-17 | 2026-09-02 | 1056 | STG-01 | Produce planned content assets in batches.
STG-03 | Editorial Review | Review, revise, and approve content for publication. | Content producer | Draft Production outputs | Editorial Review deliverables | 2026-09-03 | 2026-09-21 | 1056 | STG-02 | Review, revise, and approve content for publication.
STG-04 | Publishing Prep | Prepare final assets, captions, metadata, and schedule. | Content producer | Editorial Review outputs | Publishing Prep deliverables | 2026-09-22 | 2026-10-08 | 1056 | STG-03 | Prepare final assets, captions, metadata, and schedule.
STG-05 | Reporting | Track output, quality, and campaign performance indicators. | Content producer | Publishing Prep outputs | Reporting deliverables | 2026-10-09 | 2026-10-28 | 1056 | STG-04 | Track output, quality, and campaign performance indicators.

## Task Breakdown
Task ID | Task Name | Description | Workflow Stage | Assigned Role | Priority | Planned Start | Planned End | Estimated Hours | Planned Quantity | Production Unit | Daily Target | Dependencies | Expected Deliverable | Completion Criteria | Initial Status
TASK-001 | Content Planning work package | Define topics, channels, calendar, and approval criteria. | STG-01 | Content producer | MEDIUM | 2026-07-29 | 2026-08-14 | 1056 | 93 | video hours | 7.05 |  | Content Planning completed | Define topics, channels, calendar, and approval criteria. | NOT_STARTED
TASK-002 | Draft Production work package | Produce planned content assets in batches. | STG-02 | Content producer | MEDIUM | 2026-08-17 | 2026-09-02 | 1056 | 93 | video hours | 7.05 | TASK-001 | Draft Production completed | Produce planned content assets in batches. | NOT_STARTED
TASK-003 | Editorial Review work package | Review, revise, and approve content for publication. | STG-03 | Quality reviewer | MEDIUM | 2026-09-03 | 2026-09-21 | 1056 | 93 | video hours | 7.05 | TASK-002 | Editorial Review completed | Review, revise, and approve content for publication. | NOT_STARTED
TASK-004 | Publishing Prep work package | Prepare final assets, captions, metadata, and schedule. | STG-04 | Content producer | MEDIUM | 2026-09-22 | 2026-10-08 | 1056 | 93 | video hours | 7.05 | TASK-003 | Publishing Prep completed | Prepare final assets, captions, metadata, and schedule. | NOT_STARTED
TASK-005 | Reporting work package | Track output, quality, and campaign performance indicators. | STG-05 | Content producer | HIGH | 2026-10-09 | 2026-10-28 | 1056 | 93 | video hours | 7.05 | TASK-004 | Reporting completed | Track output, quality, and campaign performance indicators. | NOT_STARTED

## Quality Plan
Area | Method | Target | Planned Hours
Review coverage | Sampling, validation, and correction queue | Material sample reviewed before completion | 633.6
Rework handling | Track exceptions separately and recheck corrected output | No unresolved critical exceptions at closeout | 221.76

## Risk Register
Risk ID | Description | Category | Probability | Impact | Severity | Trigger | Mitigation | Contingency | Owner Role
RISK-001 | Quality review delays | content production | MEDIUM | MEDIUM | MODERATE | Progress, quality, or resource indicator moves outside threshold | Implement a buffer of 10% extra time for quality review and corrections | Use buffer and prioritize critical deliverables. | Project lead
RISK-002 | Equipment failure | content production | MEDIUM | MEDIUM | MODERATE | Progress, quality, or resource indicator moves outside threshold | Maintain backup equipment and perform regular equipment checks | Use buffer and prioritize critical deliverables. | Project lead
RISK-003 | High correction rates | content production | MEDIUM | MEDIUM | MODERATE | Progress, quality, or resource indicator moves outside threshold | Include a 10% buffer in the total production time for corrections | Use buffer and prioritize critical deliverables. | Project lead

## KPI Tracker
KPI ID | Name | Description | Formula | Unit | Target | Warning Threshold | Critical Threshold | Source Data
KPI-001 | Planned output | Total planned workload | SUM primary target column | video hours | 465 | Below daily target | Below 85% of target | Production Plan
KPI-002 | Capacity utilization | Required hours as percentage of available person-hours | requiredHours / availablePersonHours | % | 100 | 85% | 100% | Capacity Analysis
KPI-003 | Quality review allocation | Hours reserved for quality-control work | qualityReviewHours | hours | 633.6 | Below 10% of required hours | No quality allocation | Quality Plan

## Chart Specs
Chart ID | Chart Title | Chart Type | Purpose | Source Worksheet | Category Field | Value Fields | Aggregation | Filters | Display Target
CHART-001 | Planned Video hours by Day | line | Show daily production targets | Production Plan | Date | Target Video hours | sum |  | BOTH
CHART-002 | Capacity vs Required Hours | bar | Compare available and required hours | Capacity Analysis | Metric | Value | none | Available person-hours, Required hours, Buffer hours | BOTH
CHART-003 | Risk Distribution | bar | Summarize risks by impact | Risk Register | Impact | Risk ID | count |  | DASHBOARD

## Monthly Summary
Month | Planned Hours | Actual Hours | Variance | Completion Rate
Jul 2026 | 24 | 0
Aug 2026 | 147 | 0
Sep 2026 | 154 | 0
Oct 2026 | 140 | 0

## Phases & Risks
Delivery Phases & Risk Register
Phase | Objective
Content Planning | Define topics, channels, calendar, and approval criteria.
Draft Production | Produce planned content assets in batches.
Editorial Review | Review, revise, and approve content for publication.
Publishing Prep | Prepare final assets, captions, metadata, and schedule.
Reporting | Track output, quality, and campaign performance indicators.
Risk | Impact | Mitigation
Quality review delays | May cause the project to miss the 3-month deadline | Implement a buffer of 10% extra time for quality review and corrections
Equipment failure | Could halt production for several days | Maintain backup equipment and perform regular equipment checks
High correction rates | May require additional recording time beyond the planned 3 months | Include a 10% buffer in the total production time for corrections
Weekends excluded | Controls available workdays and daily target video hours | Schedule generated from normalized planning constraints.

## Assumptions
Planning Assumptions
No. | Assumption
1 | Video recording throughput rate of 50 video hours per person per working hour (industry standard for high-quality video production)
2 | All 10 recorders work consistently without breaks or downtime
3 | No holidays, weekends, or unexpected absences during the planning period
4 | Quality review and correction cycles do not cause significant delays beyond the buffer
5 | All video recordings pass initial quality checks without requiring re-recording
6 | The 3-month duration is sufficient for the project timeline with buffer for quality review
7 | Requested planning model preserved: LPB Model.
8 | Weekdays only scheduling was used.
9 | 465 video hours distributed across 66 scheduled days.
10 | Throughput: 50 video hours/person/hour (proposed by AI). Daily team target: ~4,000 video hours/day.