## Overview
Production Plan ¦ Overview
Project | Task Approval Monitoring Plan |  |  | Client | Not specified
Description | Generate me a production plan for a certain task status monitoring. The main unit of measure is the number of tasks approved. For 3 months starting this September 1, 2026, a total of 300 tasks should be achieved. Each day, there should be a target of 3 operator present. The production plan should also monitor how many tasks are rejected, in pending review, and a daily status flag whether it achieved the target number tasked approved.
Start Date | 2026-09-01 | Deadline | 2026-11-30
Schedule | Weekdays only | Scheduled Days | 65
PLANNED HOURS |  | TEAM SIZE |  | ACTUAL HOURS |  | COMPLETION
300 |  | 3 |  | 0
Plan Summary
Task Approval Monitoring Plan revision 4: Can you change the start date to September 1, 2026"? The deadline should change based on the start date and the the given timeframe of 3 months. So the deadline is 3 months afte.... Planned workload: 300 tasks from 2026-09-01 to 2026-11-30 with 3 resource(s).

## Production Plan
No. | Date | Month | Day | Planned Staff | Planned Tasks | Tasks per Person | Actual Staff | Actual Tasks Approved | Tasks per Person (Actual) | Planned Hours | Actual Hours | Variance (Tasks) | Completion Rate (%) | Status | LPB Phase | Expected Completion % | Notes
1 | 2026-09-01 | Sep 2026 | Tue | 3 | 4.62 | 1.54 | [7 empty] | Not Started |  |  | Training day: onboarding, process familiarization, calibration, and coached starter production
2 | 2026-09-02 | Sep 2026 | Wed | 3 | 4.62 | 1.54 | [7 empty] | Not Started |  |  | Training day: coached production, error correction, quality review, and workflow adjustment
3 | 2026-09-03 | Sep 2026 | Thu | 3 | 4.62 | 1.54 | [7 empty] | Not Started |  |  | Training day: coached production, error correction, quality review, and workflow adjustment
4 | 2026-09-04 | Sep 2026 | Fri | 3 | 4.62 | 1.54 | [7 empty] | Not Started |  |  | Training day: coached production, error correction, quality review, and workflow adjustment
5 | 2026-09-07 | Sep 2026 | Mon | 3 | 4.62 | 1.54 | [7 empty] | Not Started |  |  | Training day: coached production, error correction, quality review, and workflow adjustment
6 | 2026-09-08 | Sep 2026 | Tue | 3 | 4.62 | 1.54 | [7 empty] | Not Started |  |  | Training day: coached production, error correction, quality review, and workflow adjustment
7 | 2026-09-09 | Sep 2026 | Wed | 3 | 4.62 | 1.54 | [7 empty] | Not Started |  |  | Training day: coached production, error correction, quality review, and workflow adjustment
8 | 2026-09-10 | Sep 2026 | Thu | 3 | 4.62 | 1.54 | [7 empty] | Not Started |  |  | Training day: coached production, error correction, quality review, and workflow adjustment
9 | 2026-09-11 | Sep 2026 | Fri | 3 | 4.62 | 1.54 | [7 empty] | Not Started |  |  | Training day: coached production, error correction, quality review, and workflow adjustment
10 | 2026-09-14 | Sep 2026 | Mon | 3 | 4.62 | 1.54 | [7 empty] | Not Started |  |  | Training day: coached production, error correction, quality review, and workflow adjustment
11 | 2026-09-15 | Sep 2026 | Tue | 3 | 4.62 | 1.54 | [7 empty] | Not Started |  |  | Training day: coached production, error correction, quality review, and workflow adjustment
12 | 2026-09-16 | Sep 2026 | Wed | 3 | 4.62 | 1.54 | [7 empty] | Not Started |  |  | Training day: coached production, error correction, quality review, and workflow adjustment
13 | 2026-09-17 | Sep 2026 | Thu | 3 | 4.62 | 1.54 | [7 empty] | Not Started |  |  | Training day: coached production, error correction, quality review, and workflow adjustment
14 | 2026-09-18 | Sep 2026 | Fri | 3 | 4.62 | 1.54 | [7 empty] | Not Started |  |  | Training day: coached production, error correction, quality review, and workflow adjustment
15 | 2026-09-21 | Sep 2026 | Mon | 3 | 4.62 | 1.54 | [7 empty] | Not Started |  |  | Training day: coached production, error correction, quality review, and workflow adjustment
16 | 2026-09-22 | Sep 2026 | Tue | 3 | 4.62 | 1.54 | [7 empty] | Not Started |  |  | Training day: coached production, error correction, quality review, and workflow adjustment
17 | 2026-09-23 | Sep 2026 | Wed | 3 | 4.62 | 1.54 | [7 empty] | Not Started |  |  | Training day: coached production, error correction, quality review, and workflow adjustment
18 | 2026-09-24 | Sep 2026 | Thu | 3 | 4.62 | 1.54 | [7 empty] | Not Started |  |  | Training day: coached production, error correction, quality review, and workflow adjustment
19 | 2026-09-25 | Sep 2026 | Fri | 3 | 4.62 | 1.54 | [7 empty] | Not Started |  |  | Training day: coached production, error correction, quality review, and workflow adjustment
20 | 2026-09-28 | Sep 2026 | Mon | 3 | 4.62 | 1.54 | [7 empty] | Not Started |  |  | Training day: coached production, error correction, quality review, and workflow adjustment
21 | 2026-09-29 | Sep 2026 | Tue | 3 | 4.62 | 1.54 | [7 empty] | Not Started |  |  | Training day: coached production, error correction, quality review, and workflow adjustment
22 | 2026-09-30 | Sep 2026 | Wed | 3 | 4.62 | 1.54 | [7 empty] | Not Started |  |  | Training day: coached production, error correction, quality review, and workflow adjustment
23 | 2026-10-01 | Oct 2026 | Thu | 3 | 4.62 | 1.54 | [7 empty] | Not Started |  |  | Full-production day: maximize planned output while monitoring quality and workforce utilization
24 | 2026-10-02 | Oct 2026 | Fri | 3 | 4.62 | 1.54 | [7 empty] | Not Started |  |  | Full-production day: maximize planned output while monitoring quality and workforce utilization
25 | 2026-10-05 | Oct 2026 | Mon | 3 | 4.62 | 1.54 | [7 empty] | Not Started |  |  | Full-production day: maximize planned output while monitoring quality and workforce utilization
26 | 2026-10-06 | Oct 2026 | Tue | 3 | 4.62 | 1.54 | [7 empty] | Not Started |  |  | Full-production day: maximize planned output while monitoring quality and workforce utilization
27 | 2026-10-07 | Oct 2026 | Wed | 3 | 4.62 | 1.54 | [7 empty] | Not Started |  |  | Full-production day: maximize planned output while monitoring quality and workforce utilization
28 | 2026-10-08 | Oct 2026 | Thu | 3 | 4.62 | 1.54 | [7 empty] | Not Started |  |  | Full-production day: maximize planned output while monitoring quality and workforce utilization
29 | 2026-10-09 | Oct 2026 | Fri | 3 | 4.62 | 1.54 | [7 empty] | Not Started |  |  | Full-production day: maximize planned output while monitoring quality and workforce utilization
30 | 2026-10-12 | Oct 2026 | Mon | 3 | 4.62 | 1.54 | [7 empty] | Not Started |  |  | Full-production day: maximize planned output while monitoring quality and workforce utilization
31 | 2026-10-13 | Oct 2026 | Tue | 3 | 4.62 | 1.54 | [7 empty] | Not Started |  |  | Full-production day: maximize planned output while monitoring quality and workforce utilization
32 | 2026-10-14 | Oct 2026 | Wed | 3 | 4.62 | 1.54 | [7 empty] | Not Started |  |  | Full-production day: maximize planned output while monitoring quality and workforce utilization
33 | 2026-10-15 | Oct 2026 | Thu | 3 | 4.62 | 1.54 | [7 empty] | Not Started |  |  | Full-production day: maximize planned output while monitoring quality and workforce utilization
34 | 2026-10-16 | Oct 2026 | Fri | 3 | 4.62 | 1.54 | [7 empty] | Not Started |  |  | Full-production day: maximize planned output while monitoring quality and workforce utilization
35 | 2026-10-19 | Oct 2026 | Mon | 3 | 4.62 | 1.54 | [7 empty] | Not Started |  |  | Full-production day: maximize planned output while monitoring quality and workforce utilization
36 | 2026-10-20 | Oct 2026 | Tue | 3 | 4.61 | 1.54 | [7 empty] | Not Started |  |  | Full-production day: maximize planned output while monitoring quality and workforce utilization
37 | 2026-10-21 | Oct 2026 | Wed | 3 | 4.61 | 1.54 | [7 empty] | Not Started |  |  | Full-production day: maximize planned output while monitoring quality and workforce utilization
38 | 2026-10-22 | Oct 2026 | Thu | 3 | 4.61 | 1.54 | [7 empty] | Not Started |  |  | Full-production day: maximize planned output while monitoring quality and workforce utilization
39 | 2026-10-23 | Oct 2026 | Fri | 3 | 4.61 | 1.54 | [7 empty] | Not Started |  |  | Full-production day: maximize planned output while monitoring quality and workforce utilization
40 | 2026-10-26 | Oct 2026 | Mon | 3 | 4.61 | 1.54 | [7 empty] | Not Started |  |  | Full-production day: maximize planned output while monitoring quality and workforce utilization
41 | 2026-10-27 | Oct 2026 | Tue | 3 | 4.61 | 1.54 | [7 empty] | Not Started |  |  | Full-production day: maximize planned output while monitoring quality and workforce utilization
42 | 2026-10-28 | Oct 2026 | Wed | 3 | 4.61 | 1.54 | [7 empty] | Not Started |  |  | Full-production day: maximize planned output while monitoring quality and workforce utilization
43 | 2026-10-29 | Oct 2026 | Thu | 3 | 4.61 | 1.54 | [7 empty] | Not Started |  |  | Full-production day: maximize planned output while monitoring quality and workforce utilization
44 | 2026-10-30 | Oct 2026 | Fri | 3 | 4.61 | 1.54 | [7 empty] | Not Started |  |  | Full-production day: maximize planned output while monitoring quality and workforce utilization
45 | 2026-11-02 | Nov 2026 | Mon | 3 | 4.61 | 1.54 | [7 empty] | Not Started |  |  | Review day: backlog clearing, quality checks, and rework triage
46 | 2026-11-03 | Nov 2026 | Tue | 3 | 4.61 | 1.54 | [7 empty] | Not Started |  |  | Maintenance day: corrections, validation, exception resolution, and remaining production
47 | 2026-11-04 | Nov 2026 | Wed | 3 | 4.61 | 1.54 | [7 empty] | Not Started |  |  | Maintenance day: corrections, validation, exception resolution, and remaining production
48 | 2026-11-05 | Nov 2026 | Thu | 3 | 4.61 | 1.54 | [7 empty] | Not Started |  |  | Maintenance day: corrections, validation, exception resolution, and remaining production
49 | 2026-11-06 | Nov 2026 | Fri | 3 | 4.61 | 1.54 | [7 empty] | Not Started |  |  | Maintenance day: corrections, validation, exception resolution, and remaining production
50 | 2026-11-09 | Nov 2026 | Mon | 3 | 4.61 | 1.54 | [7 empty] | Not Started |  |  | Maintenance day: corrections, validation, exception resolution, and remaining production
51 | 2026-11-10 | Nov 2026 | Tue | 3 | 4.61 | 1.54 | [7 empty] | Not Started |  |  | Maintenance day: corrections, validation, exception resolution, and remaining production
52 | 2026-11-11 | Nov 2026 | Wed | 3 | 4.61 | 1.54 | [7 empty] | Not Started |  |  | Maintenance day: corrections, validation, exception resolution, and remaining production
53 | 2026-11-12 | Nov 2026 | Thu | 3 | 4.61 | 1.54 | [7 empty] | Not Started |  |  | Maintenance day: corrections, validation, exception resolution, and remaining production
54 | 2026-11-13 | Nov 2026 | Fri | 3 | 4.61 | 1.54 | [7 empty] | Not Started |  |  | Maintenance day: corrections, validation, exception resolution, and remaining production
55 | 2026-11-16 | Nov 2026 | Mon | 3 | 4.61 | 1.54 | [7 empty] | Not Started |  |  | Maintenance day: corrections, validation, exception resolution, and remaining production
56 | 2026-11-17 | Nov 2026 | Tue | 3 | 4.61 | 1.54 | [7 empty] | Not Started |  |  | Maintenance day: corrections, validation, exception resolution, and remaining production
57 | 2026-11-18 | Nov 2026 | Wed | 3 | 4.61 | 1.54 | [7 empty] | Not Started |  |  | Maintenance day: corrections, validation, exception resolution, and remaining production
58 | 2026-11-19 | Nov 2026 | Thu | 3 | 4.61 | 1.54 | [7 empty] | Not Started |  |  | Maintenance day: corrections, validation, exception resolution, and remaining production
59 | 2026-11-20 | Nov 2026 | Fri | 3 | 4.61 | 1.54 | [7 empty] | Not Started |  |  | Maintenance day: corrections, validation, exception resolution, and remaining production
60 | 2026-11-23 | Nov 2026 | Mon | 3 | 4.61 | 1.54 | [7 empty] | Not Started |  |  | Maintenance day: corrections, validation, exception resolution, and remaining production
61 | 2026-11-24 | Nov 2026 | Tue | 3 | 4.61 | 1.54 | [7 empty] | Not Started |  |  | Maintenance day: corrections, validation, exception resolution, and remaining production
62 | 2026-11-25 | Nov 2026 | Wed | 3 | 4.61 | 1.54 | [7 empty] | Not Started |  |  | Maintenance day: corrections, validation, exception resolution, and remaining production
63 | 2026-11-26 | Nov 2026 | Thu | 3 | 4.61 | 1.54 | [7 empty] | Not Started |  |  | Maintenance day: corrections, validation, exception resolution, and remaining production
64 | 2026-11-27 | Nov 2026 | Fri | 3 | 4.61 | 1.54 | [7 empty] | Not Started |  |  | Maintenance day: corrections, validation, exception resolution, and remaining production
65 | 2026-11-30 | Nov 2026 | Mon | 3 | 4.61 | 1.54 | [7 empty] | Not Started |  |  | Maintenance day: corrections, validation, exception resolution, and remaining production

## LPB Phase Summary
Phase | Duration Days | Target Share | Planned Tasks | Target Employees | Records per Employee | Target Hours | Expected Completion % | Focus
Learning | 22 | 20% | 60 | 3 | 20 | 32 | 20 | Train the team, confirm workflow rules, calibrate quality expectations, and ramp production gradually.
Performing | 22 | 50% | 150 | 3 | 50 | 80 | 70 | Run the main production workload at the highest stable target while maintaining quality standards.
Breakthrough | 22 | 30% | 90 | 3 | 30 | 48 | 100 | Complete remaining production, resolve backlogs, perform maintenance, rework exceptions, and validate final output.

## Weekly Schedule
Week | Start Date | End Date | Planned Tasks | Focus | Review Checkpoint
1 | 2026-07-29 | 2026-08-04 | 15 | Training day: onboarding, process familiarization, calibration, and coached starter production | Team lead check-in
2 | 2026-08-05 | 2026-08-11 | 15 | Training day: coached production, error correction, quality review, and workflow adjustment | Progress review and issue clearing
3 | 2026-08-12 | 2026-08-18 | 15 | Training day: coached production, error correction, quality review, and workflow adjustment | Team lead check-in
4 | 2026-08-19 | 2026-08-25 | 11 | Training day: coached production, error correction, quality review, and workflow adjustment | Progress review and issue clearing
5 | 2026-08-26 | 2026-09-01 | 25 | Training day: coached production, error correction, quality review, and workflow adjustment | Team lead check-in
6 | 2026-09-02 | 2026-09-08 | 35 | Full-production day: maximize planned output while monitoring quality and workforce utilization | Progress review and issue clearing
7 | 2026-09-09 | 2026-09-15 | 35 | Full-production day: maximize planned output while monitoring quality and workforce utilization | Team lead check-in
8 | 2026-09-16 | 2026-09-22 | 35 | Full-production day: maximize planned output while monitoring quality and workforce utilization | Progress review and issue clearing
9 | 2026-09-23 | 2026-09-29 | 29 | Full-production day: maximize planned output while monitoring quality and workforce utilization | Team lead check-in
10 | 2026-09-30 | 2026-10-06 | 21 | Maintenance day: corrections, validation, exception resolution, and remaining production | Progress review and issue clearing
11 | 2026-10-07 | 2026-10-13 | 20 | Maintenance day: corrections, validation, exception resolution, and remaining production | Team lead check-in
12 | 2026-10-14 | 2026-10-20 | 20 | Maintenance day: corrections, validation, exception resolution, and remaining production | Progress review and issue clearing
13 | 2026-10-21 | 2026-10-27 | 20 | Maintenance day: corrections, validation, exception resolution, and remaining production | Team lead check-in
14 | 2026-10-28 | 2026-10-28 | 4 | Final validation day: final QA, completion review, corrections signoff, and delivery preparation | Progress review and issue clearing

## Resource Allocation
Resource | Role | Planned Hours | Primary Focus | Notes
Task Approver 1 | Task Approver | 53.33 | Learning | Weekday allocation
Task Approver 2 | Task Approver | 53.33 | Performing | Weekday allocation
Task Approver 3 | Task Approver | 53.33 | Breakthrough | Weekday allocation

## Milestones
Milestone | Target Date | Owner | Dependency | Acceptance Check
Learning complete | 2026-08-27 | Resource 1 | Inputs confirmed | Train the team, confirm workflow rules, calibrate quality expectations, and ramp production gradually.
Performing complete | 2026-09-28 | Resource 2 | Learning complete | Run the main production workload at the highest stable target while maintaining quality standards.
Breakthrough complete | 2026-10-28 | Project lead | Performing complete | Complete remaining production, resolve backlogs, perform maintenance, rework exceptions, and validate final output.

## QA Review
Checkpoint | Date | Scope | Owner | Criteria
Week 1 quality review | 2026-08-04 | Progress review, blockers, and output completeness | Project lead | Output meets agreed rules before continuing
Week 2 quality review | 2026-08-11 | Progress review, blockers, and output completeness | Project lead | Output meets agreed rules before continuing
Week 3 quality review | 2026-08-18 | Progress review, blockers, and output completeness | Project lead | Output meets agreed rules before continuing
Week 4 quality review | 2026-08-25 | Progress review, blockers, and output completeness | Project lead | Output meets agreed rules before continuing
Week 5 quality review | 2026-09-01 | Progress review, blockers, and output completeness | Project lead | Output meets agreed rules before continuing
Week 6 quality review | 2026-09-08 | Progress review, blockers, and output completeness | Project lead | Output meets agreed rules before continuing
Week 7 quality review | 2026-09-15 | Progress review, blockers, and output completeness | Project lead | Output meets agreed rules before continuing
Week 8 quality review | 2026-09-22 | Progress review, blockers, and output completeness | Project lead | Output meets agreed rules before continuing
Week 9 quality review | 2026-09-29 | Progress review, blockers, and output completeness | Project lead | Output meets agreed rules before continuing
Week 10 quality review | 2026-10-06 | Progress review, blockers, and output completeness | Project lead | Output meets agreed rules before continuing
Week 11 quality review | 2026-10-13 | Progress review, blockers, and output completeness | Project lead | Output meets agreed rules before continuing
Week 12 quality review | 2026-10-20 | Progress review, blockers, and output completeness | Project lead | Output meets agreed rules before continuing
Week 13 quality review | 2026-10-27 | Progress review, blockers, and output completeness | Project lead | Output meets agreed rules before continuing
Final review | 2026-10-28 | Progress review, blockers, and output completeness | Project lead | Output meets agreed rules before continuing

## Risks and Assumptions
Type | Item | Impact | Mitigation / Note
Risk | Staffing shortages or unavailability | Reduces throughput and delays task approval | Maintain a buffer of 1-2 additional staff for unexpected absences.
Risk | Review process delays | Reduces daily task approval rate | Implement a dedicated review queue and prioritize urgent tasks.
Risk | Inconsistent throughput | Affects overall project timeline and resource allocation | Monitor daily performance and adjust staffing or hours as needed.
Assumption | Weekends excluded | Controls available workdays and daily target tasks | Schedule generated from normalized planning constraints.

## Progress Tracker
Period | Planned Tasks | Actual Tasks | Variance | Completion % | Status | Notes
Week 1 | 15 |  |  |  | Not Started
Week 2 | 15 |  |  |  | Not Started
Week 3 | 15 |  |  |  | Not Started
Week 4 | 11 |  |  |  | Not Started
Week 5 | 25 |  |  |  | Not Started
Week 6 | 35 |  |  |  | Not Started
Week 7 | 35 |  |  |  | Not Started
Week 8 | 35 |  |  |  | Not Started
Week 9 | 29 |  |  |  | Not Started
Week 10 | 21 |  |  |  | Not Started
Week 11 | 20 |  |  |  | Not Started
Week 12 | 20 |  |  |  | Not Started
Week 13 | 20 |  |  |  | Not Started
Week 14 | 4 |  |  |  | Not Started

## Summary
Metric | Value
Project type | manufacturing
Production unit | tasks
Start date | 2026-07-29
End date | 2026-10-28
Total planned hours | 160
Team size | 3
Schedule mode | Weekdays only
Total planned tasks | 300
LPB output split | Learning 20%, Performing 50%, Breakthrough 30%

## Project Information
Field | Value
Project category | manufacturing
Production unit | tasks
Planning model | LPB Model
Feasibility status | FEASIBLE
Requires clarification | false
Clarification questions

## Capacity Analysis
Metric | Formula | Value | Unit
Available person-hours | teamSize × workingDays × productiveHoursPerDay | 1584 | hours
Required hours | planned production hours + quality review hours | 160 | hours
Production hours | requiredHours - qualityReviewHours | 140.8 | hours
Quality review hours | max(requiredHours × 12%, scheduledDays × 0.25) | 19.2 | hours
Utilization | requiredHours ÷ availablePersonHours × 100 | 10.1 | %
Buffer hours | availablePersonHours - requiredHours | 1424 | hours
Required daily output | planned workload ÷ workingDays | 4.55 | tasks
Required output per resource per day | requiredDailyOutput ÷ teamSize | 1.52 | tasks
Feasibility status | deterministic utilization and assumption check | FEASIBLE | status

## Workflow Stages
Stage ID | Stage Name | Purpose | Owner Role | Inputs | Outputs | Planned Start | Planned End | Estimated Hours | Dependencies | Completion Criteria
STG-01 | Learning | Train the team, confirm workflow rules, calibrate quality expectations, and ramp production gradually. | Machine/operator | Project request and confirmed constraints | Learning deliverables | 2026-07-29 | 2026-08-27 | 32 |  | Train the team, confirm workflow rules, calibrate quality expectations, and ramp production gradually.
STG-02 | Performing | Run the main production workload at the highest stable target while maintaining quality standards. | Machine/operator | Learning outputs | Performing deliverables | 2026-08-28 | 2026-09-28 | 80 | STG-01 | Run the main production workload at the highest stable target while maintaining quality standards.
STG-03 | Breakthrough | Complete remaining production, resolve backlogs, perform maintenance, rework exceptions, and validate final output. | Machine/operator | Performing outputs | Breakthrough deliverables | 2026-09-29 | 2026-10-28 | 48 | STG-02 | Complete remaining production, resolve backlogs, perform maintenance, rework exceptions, and validate final output.

## Task Breakdown
Task ID | Task Name | Description | Workflow Stage | Assigned Role | Priority | Planned Start | Planned End | Estimated Hours | Planned Quantity | Production Unit | Daily Target | Dependencies | Expected Deliverable | Completion Criteria | Initial Status
TASK-001 | Training day: coached production, error correction, quality review, and workflow adjustment | Train the team, confirm workflow rules, calibrate quality expectations, and ramp production gradually. | STG-01 | Machine/operator | MEDIUM | 2026-09-01 | 2026-09-30 | 32 | 60 | tasks | 2.73 |  | Learning completed | Train the team, confirm workflow rules, calibrate quality expectations, and ramp production gradually. | NOT_STARTED
TASK-002 | Full-production day: maximize planned output while monitoring quality and workforce utilization | Run the main production workload at the highest stable target while maintaining quality standards. | STG-02 | Machine/operator | MEDIUM | 2026-10-01 | 2026-11-02 | 80 | 150 | tasks | 6.82 | TASK-001 | Performing completed | Run the main production workload at the highest stable target while maintaining quality standards. | NOT_STARTED
TASK-003 | Maintenance day: corrections, validation, exception resolution, and remaining production | Complete remaining production, resolve backlogs, perform maintenance, rework exceptions, and validate final output. | STG-03 | Machine/operator | HIGH | 2026-11-02 | 2026-11-30 | 48 | 90 | tasks | 4.09 | TASK-002 | Breakthrough completed | Complete remaining production, resolve backlogs, perform maintenance, rework exceptions, and validate final output. | NOT_STARTED

## Quality Plan
Area | Method | Target | Planned Hours
Review coverage | Batch inspection and defect isolation | Material sample reviewed before completion | 19.2
Rework handling | Track exceptions separately and recheck corrected output | No unresolved critical exceptions at closeout | 6.72

## Risk Register
Risk ID | Description | Category | Probability | Impact | Severity | Trigger | Mitigation | Contingency | Owner Role
RISK-001 | Staffing shortages or unavailability | manufacturing | MEDIUM | MEDIUM | MODERATE | Progress, quality, or resource indicator moves outside threshold | Maintain a buffer of 1-2 additional staff for unexpected absences. | Use buffer and prioritize critical deliverables. | Project lead
RISK-002 | Review process delays | manufacturing | MEDIUM | MEDIUM | MODERATE | Progress, quality, or resource indicator moves outside threshold | Implement a dedicated review queue and prioritize urgent tasks. | Use buffer and prioritize critical deliverables. | Project lead
RISK-003 | Inconsistent throughput | manufacturing | MEDIUM | MEDIUM | MODERATE | Progress, quality, or resource indicator moves outside threshold | Monitor daily performance and adjust staffing or hours as needed. | Use buffer and prioritize critical deliverables. | Project lead

## KPI Tracker
KPI ID | Name | Description | Formula | Unit | Target | Warning Threshold | Critical Threshold | Source Data
KPI-001 | Planned output | Total planned workload | SUM primary target column | tasks | 300 | Below daily target | Below 85% of target | Production Plan
KPI-002 | Capacity utilization | Required hours as percentage of available person-hours | requiredHours / availablePersonHours | % | 10.1 | 85% | 100% | Capacity Analysis
KPI-003 | Quality review allocation | Hours reserved for quality-control work | qualityReviewHours | hours | 19.2 | Below 10% of required hours | No quality allocation | Quality Plan

## Chart Specs
Chart ID | Chart Title | Chart Type | Purpose | Source Worksheet | Category Field | Value Fields | Aggregation | Filters | Display Target
CHART-001 | Planned Tasks by Day | line | Show daily production targets | Production Plan | Date | Planned Tasks | sum |  | BOTH
CHART-002 | Capacity vs Required Hours | bar | Compare available and required hours | Capacity Analysis | Metric | Value | none | Available person-hours, Required hours, Buffer hours | BOTH
CHART-003 | Risk Distribution | bar | Summarize risks by impact | Risk Register | Impact | Risk ID | count |  | DASHBOARD

## Monthly Summary
Month | Planned Hours | Actual Hours | Variance | Completion Rate
Sep 2026 | 101.64 | 0
Oct 2026 | 101.55 | 0
Nov 2026 | 96.81 | 0

## Phases & Risks
Delivery Phases & Risk Register
Phase | Objective
Learning | Complete planned production work.
Performing | Complete planned production work.
Breakthrough | Complete planned production work.
Risk | Impact | Mitigation
Staffing shortages or unavailability | Reduces throughput and delays task approval | Maintain a buffer of 1-2 additional staff for unexpected absences.
Review process delays | Reduces daily task approval rate | Implement a dedicated review queue and prioritize urgent tasks.
Inconsistent throughput | Affects overall project timeline and resource allocation | Monitor daily performance and adjust staffing or hours as needed.
Weekends excluded | Controls available workdays and daily target tasks | Schedule generated from normalized planning constraints.

## Assumptions
Planning Assumptions
No. | Assumption
1 | Throughput rate is based on industry standards for task approval processes.
2 | Staffing is fixed at 3 operators for the duration.
3 | Review and rejection are treated as active work and not free.
4 | All tasks must be reviewed before approval.
5 | The LPB Model is applied to ensure linear progress and risk alignment.
6 | Requested planning model preserved: LPB Model.
7 | LPB phase boundaries divide scheduled workdays into approximately equal thirds with output/effort targets of 20%, 50%, and 30%.
8 | Weekdays only scheduling was used.
9 | 300 tasks distributed with LPB allocation: Learning 20%, Performing 50%, Breakthrough 30%.
10 | Throughput: 2 tasks/person/hour (proposed by AI). Daily team target: ~48 tasks/day.
11 | Revision 2: The deadline should change based on the start date and the the given timeframe of 3 months. So the deadline is 3 months after the startdate. The staffing and everything else sho...
12 | Revision 3: Can you change the start date to September 1, 2026"? The deadline should change based on the start date and the the given timeframe of 3 months. So the deadline is 3 months afte...
13 | Revision 4: Can you change the start date to September 1, 2026"? The deadline should change based on the start date and the the given timeframe of 3 months. So the deadline is 3 months afte...