## Overview
Production Plan ¦ Overview
Project | API Check Annotation Capacity Plan 2026-07-29T06-56-34-330Z |  |  | Client | Internal
Description | Create a production plan for four annotators with 120 total hours over 50 weekdays.
Start Date | 2026-07-29 | Deadline | 2026-10-06
Schedule | Weekdays only | Scheduled Days | 50
PLANNED HOURS |  | TEAM SIZE |  | ACTUAL HOURS |  | COMPLETION
480 |  | 4 |  | 0
Plan Summary
API Check Annotation Capacity Plan 2026-07-29T06-56-34-330Z revision 2: The 120 hours should be for each annotator, not the entire team.. Planned workload: 480 hours from 2026-07-29 to 2026-10-06 with 4 resource(s).

## Production Plan
No. | Date | Month | Day | Target Active Annotators | Target Total Hours | Target Total Hours per Annotator | Actual Active Annotators | Actual Total Hours | Actual Total Hours per Annotator | Target Hours | Actual Hours | Total Variance | Completion Rate (%) | Status | Notes
1 | 2026-07-29 | Jul 2026 | Wed | 4 | 9.6 | 2.4 |  |  |  | 9.6 |  |  |  | Not Started | Guideline Setup batch annotation
2 | 2026-07-30 | Jul 2026 | Thu | 4 | 9.6 | 2.4 |  |  |  | 9.6 |  |  |  | Not Started | Guideline Setup batch annotation
3 | 2026-07-31 | Jul 2026 | Fri | 4 | 9.6 | 2.4 |  |  |  | 9.6 |  |  |  | Not Started | Guideline Setup batch annotation
4 | 2026-08-03 | Aug 2026 | Mon | 4 | 9.6 | 2.4 |  |  |  | 9.6 |  |  |  | Not Started | Guideline Setup batch annotation
5 | 2026-08-04 | Aug 2026 | Tue | 4 | 9.6 | 2.4 |  |  |  | 9.6 |  |  |  | Not Started | Guideline Setup batch annotation
6 | 2026-08-05 | Aug 2026 | Wed | 4 | 9.6 | 2.4 |  |  |  | 9.6 |  |  |  | Not Started | Guideline Setup batch annotation
7 | 2026-08-06 | Aug 2026 | Thu | 4 | 9.6 | 2.4 |  |  |  | 9.6 |  |  |  | Not Started | Guideline Setup batch annotation
8 | 2026-08-07 | Aug 2026 | Fri | 4 | 9.6 | 2.4 |  |  |  | 9.6 |  |  |  | Not Started | Guideline Setup batch annotation
9 | 2026-08-10 | Aug 2026 | Mon | 4 | 9.6 | 2.4 |  |  |  | 9.6 |  |  |  | Not Started | Guideline Setup batch annotation
10 | 2026-08-11 | Aug 2026 | Tue | 4 | 9.6 | 2.4 |  |  |  | 9.6 |  |  |  | Not Started | Guideline Setup batch annotation
11 | 2026-08-12 | Aug 2026 | Wed | 4 | 9.6 | 2.4 |  |  |  | 9.6 |  |  |  | Not Started | Pilot Annotation batch annotation
12 | 2026-08-13 | Aug 2026 | Thu | 4 | 9.6 | 2.4 |  |  |  | 9.6 |  |  |  | Not Started | Pilot Annotation batch annotation
13 | 2026-08-14 | Aug 2026 | Fri | 4 | 9.6 | 2.4 |  |  |  | 9.6 |  |  |  | Not Started | Pilot Annotation batch annotation
14 | 2026-08-17 | Aug 2026 | Mon | 4 | 9.6 | 2.4 |  |  |  | 9.6 |  |  |  | Not Started | Pilot Annotation batch annotation
15 | 2026-08-18 | Aug 2026 | Tue | 4 | 9.6 | 2.4 |  |  |  | 9.6 |  |  |  | Not Started | Pilot Annotation batch annotation
16 | 2026-08-19 | Aug 2026 | Wed | 4 | 9.6 | 2.4 |  |  |  | 9.6 |  |  |  | Not Started | Pilot Annotation batch annotation
17 | 2026-08-20 | Aug 2026 | Thu | 4 | 9.6 | 2.4 |  |  |  | 9.6 |  |  |  | Not Started | Pilot Annotation batch annotation
18 | 2026-08-21 | Aug 2026 | Fri | 4 | 9.6 | 2.4 |  |  |  | 9.6 |  |  |  | Not Started | Pilot Annotation batch annotation
19 | 2026-08-24 | Aug 2026 | Mon | 4 | 9.6 | 2.4 |  |  |  | 9.6 |  |  |  | Not Started | Pilot Annotation batch annotation
20 | 2026-08-25 | Aug 2026 | Tue | 4 | 9.6 | 2.4 |  |  |  | 9.6 |  |  |  | Not Started | Pilot Annotation batch annotation
21 | 2026-08-26 | Aug 2026 | Wed | 4 | 9.6 | 2.4 |  |  |  | 9.6 |  |  |  | Not Started | Production Annotation batch annotation
22 | 2026-08-27 | Aug 2026 | Thu | 4 | 9.6 | 2.4 |  |  |  | 9.6 |  |  |  | Not Started | Production Annotation batch annotation
23 | 2026-08-28 | Aug 2026 | Fri | 4 | 9.6 | 2.4 |  |  |  | 9.6 |  |  |  | Not Started | Production Annotation batch annotation
24 | 2026-08-31 | Aug 2026 | Mon | 4 | 9.6 | 2.4 |  |  |  | 9.6 |  |  |  | Not Started | Production Annotation batch annotation
25 | 2026-09-01 | Sep 2026 | Tue | 4 | 9.6 | 2.4 |  |  |  | 9.6 |  |  |  | Not Started | Production Annotation batch annotation
26 | 2026-09-02 | Sep 2026 | Wed | 4 | 9.6 | 2.4 |  |  |  | 9.6 |  |  |  | Not Started | Production Annotation batch annotation
27 | 2026-09-03 | Sep 2026 | Thu | 4 | 9.6 | 2.4 |  |  |  | 9.6 |  |  |  | Not Started | Production Annotation batch annotation
28 | 2026-09-04 | Sep 2026 | Fri | 4 | 9.6 | 2.4 |  |  |  | 9.6 |  |  |  | Not Started | Production Annotation batch annotation
29 | 2026-09-07 | Sep 2026 | Mon | 4 | 9.6 | 2.4 |  |  |  | 9.6 |  |  |  | Not Started | Production Annotation batch annotation
30 | 2026-09-08 | Sep 2026 | Tue | 4 | 9.6 | 2.4 |  |  |  | 9.6 |  |  |  | Not Started | Production Annotation batch annotation
31 | 2026-09-09 | Sep 2026 | Wed | 4 | 9.6 | 2.4 |  |  |  | 9.6 |  |  |  | Not Started | QA sample and adjudicate annotation output
32 | 2026-09-10 | Sep 2026 | Thu | 4 | 9.6 | 2.4 |  |  |  | 9.6 |  |  |  | Not Started | QA sample and adjudicate annotation output
33 | 2026-09-11 | Sep 2026 | Fri | 4 | 9.6 | 2.4 |  |  |  | 9.6 |  |  |  | Not Started | QA sample and adjudicate annotation output
34 | 2026-09-14 | Sep 2026 | Mon | 4 | 9.6 | 2.4 |  |  |  | 9.6 |  |  |  | Not Started | QA sample and adjudicate annotation output
35 | 2026-09-15 | Sep 2026 | Tue | 4 | 9.6 | 2.4 |  |  |  | 9.6 |  |  |  | Not Started | QA sample and adjudicate annotation output
36 | 2026-09-16 | Sep 2026 | Wed | 4 | 9.6 | 2.4 |  |  |  | 9.6 |  |  |  | Not Started | QA sample and adjudicate annotation output
37 | 2026-09-17 | Sep 2026 | Thu | 4 | 9.6 | 2.4 |  |  |  | 9.6 |  |  |  | Not Started | QA sample and adjudicate annotation output
38 | 2026-09-18 | Sep 2026 | Fri | 4 | 9.6 | 2.4 |  |  |  | 9.6 |  |  |  | Not Started | QA sample and adjudicate annotation output
39 | 2026-09-21 | Sep 2026 | Mon | 4 | 9.6 | 2.4 |  |  |  | 9.6 |  |  |  | Not Started | QA sample and adjudicate annotation output
40 | 2026-09-22 | Sep 2026 | Tue | 4 | 9.6 | 2.4 |  |  |  | 9.6 |  |  |  | Not Started | QA sample and adjudicate annotation output
41 | 2026-09-23 | Sep 2026 | Wed | 4 | 9.6 | 2.4 |  |  |  | 9.6 |  |  |  | Not Started | Review & Delivery batch annotation
42 | 2026-09-24 | Sep 2026 | Thu | 4 | 9.6 | 2.4 |  |  |  | 9.6 |  |  |  | Not Started | Review & Delivery batch annotation
43 | 2026-09-25 | Sep 2026 | Fri | 4 | 9.6 | 2.4 |  |  |  | 9.6 |  |  |  | Not Started | Review & Delivery batch annotation
44 | 2026-09-28 | Sep 2026 | Mon | 4 | 9.6 | 2.4 |  |  |  | 9.6 |  |  |  | Not Started | Review & Delivery batch annotation
45 | 2026-09-29 | Sep 2026 | Tue | 4 | 9.6 | 2.4 |  |  |  | 9.6 |  |  |  | Not Started | Review & Delivery batch annotation
46 | 2026-09-30 | Sep 2026 | Wed | 4 | 9.6 | 2.4 |  |  |  | 9.6 |  |  |  | Not Started | Review & Delivery batch annotation
47 | 2026-10-01 | Oct 2026 | Thu | 4 | 9.6 | 2.4 |  |  |  | 9.6 |  |  |  | Not Started | Review & Delivery batch annotation
48 | 2026-10-02 | Oct 2026 | Fri | 4 | 9.6 | 2.4 |  |  |  | 9.6 |  |  |  | Not Started | Review & Delivery batch annotation
49 | 2026-10-05 | Oct 2026 | Mon | 4 | 9.6 | 2.4 |  |  |  | 9.6 |  |  |  | Not Started | Review & Delivery batch annotation
50 | 2026-10-06 | Oct 2026 | Tue | 4 | 9.6 | 2.4 |  |  |  | 9.6 |  |  |  | Not Started | Review & Delivery batch annotation

## Weekly Schedule
Week | Start Date | End Date | Planned Hours | Focus | Review Checkpoint
1 | 2026-07-29 | 2026-08-04 | 12 | Guideline Setup batch annotation | Team lead check-in
2 | 2026-08-05 | 2026-08-11 | 12 | Guideline Setup batch annotation | Progress review and issue clearing
3 | 2026-08-12 | 2026-08-18 | 12 | Pilot Annotation batch annotation | Team lead check-in
4 | 2026-08-19 | 2026-08-25 | 12 | Pilot Annotation batch annotation | Progress review and issue clearing
5 | 2026-08-26 | 2026-09-01 | 12 | Production Annotation batch annotation | Team lead check-in
6 | 2026-09-02 | 2026-09-08 | 12 | Production Annotation batch annotation | Progress review and issue clearing
7 | 2026-09-09 | 2026-09-15 | 12 | QA sample and adjudicate annotation output | Team lead check-in
8 | 2026-09-16 | 2026-09-22 | 12 | QA sample and adjudicate annotation output | Progress review and issue clearing
9 | 2026-09-23 | 2026-09-29 | 12 | Review & Delivery batch annotation | Team lead check-in
10 | 2026-09-30 | 2026-10-06 | 12 | Review & Delivery batch annotation | Progress review and issue clearing

## Resource Allocation
Resource | Role | Planned Hours | Primary Focus | Notes
Resource 1 | Annotator | 30 | Guideline Setup | Weekday allocation
Resource 2 | Annotator | 30 | Pilot Annotation | Weekday allocation
Resource 3 | Annotator | 30 | Production Annotation | Weekday allocation
Resource 4 | Annotator | 30 | QA Sampling | Weekday allocation

## Milestones
Milestone | Target Date | Owner | Dependency | Acceptance Check
Guideline Setup complete | 2026-08-11 | Resource 1 | Inputs confirmed | Finalize annotation rules, examples, and acceptance criteria.
Pilot Annotation complete | 2026-08-25 | Resource 2 | Guideline Setup complete | Run a small batch to calibrate annotators and detect ambiguity.
Production Annotation complete | 2026-09-08 | Resource 3 | Pilot Annotation complete | Complete the main annotation workload at target throughput.
QA Sampling complete | 2026-09-22 | Resource 4 | Production Annotation complete | Sample completed work and resolve quality issues.
Review & Delivery complete | 2026-10-06 | Project lead | QA Sampling complete | Review metrics, apply corrections, and package outputs.

## QA Review
Checkpoint | Date | Scope | Owner | Criteria
Week 1 quality review | 2026-08-04 | QA sample, findings review, and correction queue | Project lead | Output meets agreed rules before continuing
Week 2 quality review | 2026-08-11 | QA sample, findings review, and correction queue | Project lead | Output meets agreed rules before continuing
Week 3 quality review | 2026-08-18 | QA sample, findings review, and correction queue | Project lead | Output meets agreed rules before continuing
Week 4 quality review | 2026-08-25 | QA sample, findings review, and correction queue | Project lead | Output meets agreed rules before continuing
Week 5 quality review | 2026-09-01 | QA sample, findings review, and correction queue | Project lead | Output meets agreed rules before continuing
Week 6 quality review | 2026-09-08 | QA sample, findings review, and correction queue | Project lead | Output meets agreed rules before continuing
Week 7 quality review | 2026-09-15 | QA sample, findings review, and correction queue | Project lead | Output meets agreed rules before continuing
Week 8 quality review | 2026-09-22 | QA sample, findings review, and correction queue | Project lead | Output meets agreed rules before continuing
Week 9 quality review | 2026-09-29 | QA sample, findings review, and correction queue | Project lead | Output meets agreed rules before continuing
Final review | 2026-10-06 | QA sample, findings review, and correction queue | Project lead | Output meets agreed rules before continuing

## Risks and Assumptions
Type | Item | Impact | Mitigation / Note
Risk | Actual productivity may differ from planning assumptions. | MEDIUM | Track progress daily and escalate blockers early.
Risk | Quality findings may require rework near the deadline. | HIGH | Reserve explicit review and correction time.
Assumption | Weekends excluded | Controls available workdays and daily target hours | Schedule generated from normalized planning constraints.

## Progress Tracker
Period | Planned Hours | Actual Hours | Variance | Completion % | Status | Notes
Week 1 | 12 |  |  |  | Not Started
Week 2 | 12 |  |  |  | Not Started
Week 3 | 12 |  |  |  | Not Started
Week 4 | 12 |  |  |  | Not Started
Week 5 | 12 |  |  |  | Not Started
Week 6 | 12 |  |  |  | Not Started
Week 7 | 12 |  |  |  | Not Started
Week 8 | 12 |  |  |  | Not Started
Week 9 | 12 |  |  |  | Not Started
Week 10 | 12 |  |  |  | Not Started

## Summary
Metric | Value
Project type | annotation
Production unit | hours
Start date | 2026-07-29
End date | 2026-10-06
Total planned hours | 120
Team size | 4
Schedule mode | Weekdays only

## Project Information
Field | Value
Project category | annotation
Production unit | hours
Planning model | Not specified
Feasibility status | FEASIBLE
Requires clarification | false
Clarification questions

## Capacity Analysis
Metric | Formula | Value | Unit
Available person-hours | teamSize × workingDays × productiveHoursPerDay | 1600 | hours
Required hours | planned production hours + quality review hours | 120 | hours
Production hours | requiredHours - qualityReviewHours | 105.6 | hours
Quality review hours | max(requiredHours × 12%, scheduledDays × 0.25) | 14.4 | hours
Utilization | requiredHours ÷ availablePersonHours × 100 | 7.5 | %
Buffer hours | availablePersonHours - requiredHours | 1480 | hours
Required daily output | planned workload ÷ workingDays | 2.4 | hours
Required output per resource per day | requiredDailyOutput ÷ teamSize | 0.6 | hours
Feasibility status | deterministic utilization and assumption check | FEASIBLE | status

## Workflow Stages
Stage ID | Stage Name | Purpose | Owner Role | Inputs | Outputs | Planned Start | Planned End | Estimated Hours | Dependencies | Completion Criteria
STG-01 | Guideline Setup | Finalize annotation rules, examples, and acceptance criteria. | Annotator | Project request and confirmed constraints | Guideline Setup deliverables | 2026-07-29 | 2026-08-11 | 24 |  | Finalize annotation rules, examples, and acceptance criteria.
STG-02 | Pilot Annotation | Run a small batch to calibrate annotators and detect ambiguity. | Annotator | Guideline Setup outputs | Pilot Annotation deliverables | 2026-08-12 | 2026-08-25 | 24 | STG-01 | Run a small batch to calibrate annotators and detect ambiguity.
STG-03 | Production Annotation | Complete the main annotation workload at target throughput. | Annotator | Pilot Annotation outputs | Production Annotation deliverables | 2026-08-26 | 2026-09-08 | 24 | STG-02 | Complete the main annotation workload at target throughput.
STG-04 | QA Sampling | Sample completed work and resolve quality issues. | Annotator | Production Annotation outputs | QA Sampling deliverables | 2026-09-09 | 2026-09-22 | 24 | STG-03 | Sample completed work and resolve quality issues.
STG-05 | Review & Delivery | Review metrics, apply corrections, and package outputs. | Annotator | QA Sampling outputs | Review & Delivery deliverables | 2026-09-23 | 2026-10-06 | 24 | STG-04 | Review metrics, apply corrections, and package outputs.

## Task Breakdown
Task ID | Task Name | Description | Workflow Stage | Assigned Role | Priority | Planned Start | Planned End | Estimated Hours | Planned Quantity | Production Unit | Daily Target | Dependencies | Expected Deliverable | Completion Criteria | Initial Status
TASK-001 | Guideline Setup batch annotation | Finalize annotation rules, examples, and acceptance criteria. | STG-01 | Annotator | MEDIUM | 2026-07-29 | 2026-08-11 | 24 | 24 | hours | 2.4 |  | Guideline Setup completed | Finalize annotation rules, examples, and acceptance criteria. | NOT_STARTED
TASK-002 | Pilot Annotation batch annotation | Run a small batch to calibrate annotators and detect ambiguity. | STG-02 | Annotator | MEDIUM | 2026-08-12 | 2026-08-25 | 24 | 24 | hours | 2.4 | TASK-001 | Pilot Annotation completed | Run a small batch to calibrate annotators and detect ambiguity. | NOT_STARTED
TASK-003 | Production Annotation batch annotation | Complete the main annotation workload at target throughput. | STG-03 | Annotator | MEDIUM | 2026-08-26 | 2026-09-08 | 24 | 24 | hours | 2.4 | TASK-002 | Production Annotation completed | Complete the main annotation workload at target throughput. | NOT_STARTED
TASK-004 | QA sample and adjudicate annotation output | Sample completed work and resolve quality issues. | STG-04 | Quality reviewer | MEDIUM | 2026-09-09 | 2026-09-22 | 24 | 24 | hours | 2.4 | TASK-003 | QA Sampling completed | Sample completed work and resolve quality issues. | NOT_STARTED
TASK-005 | Review & Delivery batch annotation | Review metrics, apply corrections, and package outputs. | STG-05 | Quality reviewer | HIGH | 2026-09-23 | 2026-10-06 | 24 | 24 | hours | 2.4 | TASK-004 | Review & Delivery completed | Review metrics, apply corrections, and package outputs. | NOT_STARTED

## Quality Plan
Area | Method | Target | Planned Hours
Review coverage | Sampling, validation, and correction queue | Material sample reviewed before completion | 14.4
Rework handling | Track exceptions separately and recheck corrected output | No unresolved critical exceptions at closeout | 5.04

## Risk Register
Risk ID | Description | Category | Probability | Impact | Severity | Trigger | Mitigation | Contingency | Owner Role
RISK-001 | Actual productivity may differ from planning assumptions. | annotation | MEDIUM | MEDIUM | MODERATE | Progress, quality, or resource indicator moves outside threshold | Track progress daily and escalate blockers early. | Use buffer and prioritize critical deliverables. | Project lead
RISK-002 | Quality findings may require rework near the deadline. | annotation | MEDIUM | HIGH | HIGH | Progress, quality, or resource indicator moves outside threshold | Reserve explicit review and correction time. | Use buffer and prioritize critical deliverables. | Project lead

## KPI Tracker
KPI ID | Name | Description | Formula | Unit | Target | Warning Threshold | Critical Threshold | Source Data
KPI-001 | Planned output | Total planned workload | SUM primary target column | hours | 120 | Below daily target | Below 85% of target | Production Plan
KPI-002 | Capacity utilization | Required hours as percentage of available person-hours | requiredHours / availablePersonHours | % | 7.5 | 85% | 100% | Capacity Analysis
KPI-003 | Quality review allocation | Hours reserved for quality-control work | qualityReviewHours | hours | 14.4 | Below 10% of required hours | No quality allocation | Quality Plan

## Chart Specs
Chart ID | Chart Title | Chart Type | Purpose | Source Worksheet | Category Field | Value Fields | Aggregation | Filters | Display Target
CHART-001 | Planned Hours by Day | line | Show daily production targets | Production Plan | Date | Target Total Hours | sum |  | BOTH
CHART-002 | Capacity vs Required Hours | bar | Compare available and required hours | Capacity Analysis | Metric | Value | none | Available person-hours, Required hours, Buffer hours | BOTH
CHART-003 | Risk Distribution | bar | Summarize risks by impact | Risk Register | Impact | Risk ID | count |  | DASHBOARD

## Monthly Summary
Month | Planned Hours | Actual Hours | Variance | Completion Rate
Jul 2026 | 28.8 | 0
Aug 2026 | 201.6 | 0
Sep 2026 | 211.2 | 0
Oct 2026 | 38.4 | 0

## Phases & Risks
Delivery Phases & Risk Register
Phase | Objective
Guideline Setup | Finalize annotation rules, examples, and acceptance criteria.
Pilot Annotation | Run a small batch to calibrate annotators and detect ambiguity.
Production Annotation | Complete the main annotation workload at target throughput.
QA Sampling | Sample completed work and resolve quality issues.
Review & Delivery | Review metrics, apply corrections, and package outputs.
Risk | Impact | Mitigation
Actual productivity may differ from planning assumptions. | MEDIUM | Track progress daily and escalate blockers early.
Quality findings may require rework near the deadline. | HIGH | Reserve explicit review and correction time.
Weekends excluded | Controls available workdays and daily target hours | Schedule generated from normalized planning constraints.

## Assumptions
Planning Assumptions
No. | Assumption
1 | Weekdays only scheduling was used.
2 | Created by isolated API workflow check.
3 | Weekdays only scheduling was used.
4 | Total target hours are distributed across 50 scheduled days.
5 | Revision 2: The 120 hours should be for each annotator, not the entire team.