## Executive Summary
Production Plan ¦ Executive Summary
Project | Four-Month Annotation Production Plan |  |  | Client | Example Client
Description | Create a production plan for a class of 4 annotators over 4 calendar months with 400 total hours, starting 2026-08-01.
Start Date | 2026-08-01 | Deadline | 2026-11-30
Schedule | Calendar days | Scheduled Days | 122
PLANNED HOURS |  | TEAM SIZE |  | ACTUAL HOURS |  | COMPLETION
400 |  | 4 |  | 0
Plan Summary
A four-month, calendar-day production plan for four annotators with exactly 400 planned hours, supported by editable actuals, monthly rollups, phases, risks, and assumptions.

## Production Plan
No. | Date | Month | Day | Target Active Annotators | Target Total Hours | Target Total Hours per Annotator | Actual Active Annotators | Actual Total Hours | Actual Total Hours per Annotator | Target Hours | Actual Hours | Total Variance | Completion Rate (%) | Status | Notes
1 | 2026-08-01 | Aug 2026 | Sat | 4 | 3.28 | 0.82 |  |  |  | 3.28 |  |  |  | Not Started
2 | 2026-08-02 | Aug 2026 | Sun | 4 | 3.28 | 0.82 |  |  |  | 3.28 |  |  |  | Not Started
3 | 2026-08-03 | Aug 2026 | Mon | 4 | 3.28 | 0.82 |  |  |  | 3.28 |  |  |  | Not Started
4 | 2026-08-04 | Aug 2026 | Tue | 4 | 3.28 | 0.82 |  |  |  | 3.28 |  |  |  | Not Started
5 | 2026-08-05 | Aug 2026 | Wed | 4 | 3.28 | 0.82 |  |  |  | 3.28 |  |  |  | Not Started
6 | 2026-08-06 | Aug 2026 | Thu | 4 | 3.28 | 0.82 |  |  |  | 3.28 |  |  |  | Not Started
7 | 2026-08-07 | Aug 2026 | Fri | 4 | 3.28 | 0.82 |  |  |  | 3.28 |  |  |  | Not Started
8 | 2026-08-08 | Aug 2026 | Sat | 4 | 3.28 | 0.82 |  |  |  | 3.28 |  |  |  | Not Started
9 | 2026-08-09 | Aug 2026 | Sun | 4 | 3.28 | 0.82 |  |  |  | 3.28 |  |  |  | Not Started
10 | 2026-08-10 | Aug 2026 | Mon | 4 | 3.28 | 0.82 |  |  |  | 3.28 |  |  |  | Not Started
11 | 2026-08-11 | Aug 2026 | Tue | 4 | 3.28 | 0.82 |  |  |  | 3.28 |  |  |  | Not Started
12 | 2026-08-12 | Aug 2026 | Wed | 4 | 3.28 | 0.82 |  |  |  | 3.28 |  |  |  | Not Started
13 | 2026-08-13 | Aug 2026 | Thu | 4 | 3.28 | 0.82 |  |  |  | 3.28 |  |  |  | Not Started
14 | 2026-08-14 | Aug 2026 | Fri | 4 | 3.28 | 0.82 |  |  |  | 3.28 |  |  |  | Not Started
15 | 2026-08-15 | Aug 2026 | Sat | 4 | 3.28 | 0.82 |  |  |  | 3.28 |  |  |  | Not Started
16 | 2026-08-16 | Aug 2026 | Sun | 4 | 3.28 | 0.82 |  |  |  | 3.28 |  |  |  | Not Started
17 | 2026-08-17 | Aug 2026 | Mon | 4 | 3.28 | 0.82 |  |  |  | 3.28 |  |  |  | Not Started
18 | 2026-08-18 | Aug 2026 | Tue | 4 | 3.28 | 0.82 |  |  |  | 3.28 |  |  |  | Not Started
19 | 2026-08-19 | Aug 2026 | Wed | 4 | 3.28 | 0.82 |  |  |  | 3.28 |  |  |  | Not Started
20 | 2026-08-20 | Aug 2026 | Thu | 4 | 3.28 | 0.82 |  |  |  | 3.28 |  |  |  | Not Started
21 | 2026-08-21 | Aug 2026 | Fri | 4 | 3.28 | 0.82 |  |  |  | 3.28 |  |  |  | Not Started
22 | 2026-08-22 | Aug 2026 | Sat | 4 | 3.28 | 0.82 |  |  |  | 3.28 |  |  |  | Not Started
23 | 2026-08-23 | Aug 2026 | Sun | 4 | 3.28 | 0.82 |  |  |  | 3.28 |  |  |  | Not Started
24 | 2026-08-24 | Aug 2026 | Mon | 4 | 3.28 | 0.82 |  |  |  | 3.28 |  |  |  | Not Started
25 | 2026-08-25 | Aug 2026 | Tue | 4 | 3.28 | 0.82 |  |  |  | 3.28 |  |  |  | Not Started
26 | 2026-08-26 | Aug 2026 | Wed | 4 | 3.28 | 0.82 |  |  |  | 3.28 |  |  |  | Not Started
27 | 2026-08-27 | Aug 2026 | Thu | 4 | 3.28 | 0.82 |  |  |  | 3.28 |  |  |  | Not Started
28 | 2026-08-28 | Aug 2026 | Fri | 4 | 3.28 | 0.82 |  |  |  | 3.28 |  |  |  | Not Started
29 | 2026-08-29 | Aug 2026 | Sat | 4 | 3.28 | 0.82 |  |  |  | 3.28 |  |  |  | Not Started
30 | 2026-08-30 | Aug 2026 | Sun | 4 | 3.28 | 0.82 |  |  |  | 3.28 |  |  |  | Not Started
31 | 2026-08-31 | Aug 2026 | Mon | 4 | 3.28 | 0.82 |  |  |  | 3.28 |  |  |  | Not Started
32 | 2026-09-01 | Sep 2026 | Tue | 4 | 3.28 | 0.82 |  |  |  | 3.28 |  |  |  | Not Started
33 | 2026-09-02 | Sep 2026 | Wed | 4 | 3.28 | 0.82 |  |  |  | 3.28 |  |  |  | Not Started
34 | 2026-09-03 | Sep 2026 | Thu | 4 | 3.28 | 0.82 |  |  |  | 3.28 |  |  |  | Not Started
35 | 2026-09-04 | Sep 2026 | Fri | 4 | 3.28 | 0.82 |  |  |  | 3.28 |  |  |  | Not Started
36 | 2026-09-05 | Sep 2026 | Sat | 4 | 3.28 | 0.82 |  |  |  | 3.28 |  |  |  | Not Started
37 | 2026-09-06 | Sep 2026 | Sun | 4 | 3.28 | 0.82 |  |  |  | 3.28 |  |  |  | Not Started
38 | 2026-09-07 | Sep 2026 | Mon | 4 | 3.28 | 0.82 |  |  |  | 3.28 |  |  |  | Not Started
39 | 2026-09-08 | Sep 2026 | Tue | 4 | 3.28 | 0.82 |  |  |  | 3.28 |  |  |  | Not Started
40 | 2026-09-09 | Sep 2026 | Wed | 4 | 3.28 | 0.82 |  |  |  | 3.28 |  |  |  | Not Started
41 | 2026-09-10 | Sep 2026 | Thu | 4 | 3.28 | 0.82 |  |  |  | 3.28 |  |  |  | Not Started
42 | 2026-09-11 | Sep 2026 | Fri | 4 | 3.28 | 0.82 |  |  |  | 3.28 |  |  |  | Not Started
43 | 2026-09-12 | Sep 2026 | Sat | 4 | 3.28 | 0.82 |  |  |  | 3.28 |  |  |  | Not Started
44 | 2026-09-13 | Sep 2026 | Sun | 4 | 3.28 | 0.82 |  |  |  | 3.28 |  |  |  | Not Started
45 | 2026-09-14 | Sep 2026 | Mon | 4 | 3.28 | 0.82 |  |  |  | 3.28 |  |  |  | Not Started
46 | 2026-09-15 | Sep 2026 | Tue | 4 | 3.28 | 0.82 |  |  |  | 3.28 |  |  |  | Not Started
47 | 2026-09-16 | Sep 2026 | Wed | 4 | 3.28 | 0.82 |  |  |  | 3.28 |  |  |  | Not Started
48 | 2026-09-17 | Sep 2026 | Thu | 4 | 3.28 | 0.82 |  |  |  | 3.28 |  |  |  | Not Started
49 | 2026-09-18 | Sep 2026 | Fri | 4 | 3.28 | 0.82 |  |  |  | 3.28 |  |  |  | Not Started
50 | 2026-09-19 | Sep 2026 | Sat | 4 | 3.28 | 0.82 |  |  |  | 3.28 |  |  |  | Not Started
51 | 2026-09-20 | Sep 2026 | Sun | 4 | 3.28 | 0.82 |  |  |  | 3.28 |  |  |  | Not Started
52 | 2026-09-21 | Sep 2026 | Mon | 4 | 3.28 | 0.82 |  |  |  | 3.28 |  |  |  | Not Started
53 | 2026-09-22 | Sep 2026 | Tue | 4 | 3.28 | 0.82 |  |  |  | 3.28 |  |  |  | Not Started
54 | 2026-09-23 | Sep 2026 | Wed | 4 | 3.28 | 0.82 |  |  |  | 3.28 |  |  |  | Not Started
55 | 2026-09-24 | Sep 2026 | Thu | 4 | 3.28 | 0.82 |  |  |  | 3.28 |  |  |  | Not Started
56 | 2026-09-25 | Sep 2026 | Fri | 4 | 3.28 | 0.82 |  |  |  | 3.28 |  |  |  | Not Started
57 | 2026-09-26 | Sep 2026 | Sat | 4 | 3.28 | 0.82 |  |  |  | 3.28 |  |  |  | Not Started
58 | 2026-09-27 | Sep 2026 | Sun | 4 | 3.28 | 0.82 |  |  |  | 3.28 |  |  |  | Not Started
59 | 2026-09-28 | Sep 2026 | Mon | 4 | 3.28 | 0.82 |  |  |  | 3.28 |  |  |  | Not Started
60 | 2026-09-29 | Sep 2026 | Tue | 4 | 3.28 | 0.82 |  |  |  | 3.28 |  |  |  | Not Started
61 | 2026-09-30 | Sep 2026 | Wed | 4 | 3.28 | 0.82 |  |  |  | 3.28 |  |  |  | Not Started
62 | 2026-10-01 | Oct 2026 | Thu | 4 | 3.28 | 0.82 |  |  |  | 3.28 |  |  |  | Not Started
63 | 2026-10-02 | Oct 2026 | Fri | 4 | 3.28 | 0.82 |  |  |  | 3.28 |  |  |  | Not Started
64 | 2026-10-03 | Oct 2026 | Sat | 4 | 3.28 | 0.82 |  |  |  | 3.28 |  |  |  | Not Started
65 | 2026-10-04 | Oct 2026 | Sun | 4 | 3.28 | 0.82 |  |  |  | 3.28 |  |  |  | Not Started
66 | 2026-10-05 | Oct 2026 | Mon | 4 | 3.28 | 0.82 |  |  |  | 3.28 |  |  |  | Not Started
67 | 2026-10-06 | Oct 2026 | Tue | 4 | 3.28 | 0.82 |  |  |  | 3.28 |  |  |  | Not Started
68 | 2026-10-07 | Oct 2026 | Wed | 4 | 3.28 | 0.82 |  |  |  | 3.28 |  |  |  | Not Started
69 | 2026-10-08 | Oct 2026 | Thu | 4 | 3.28 | 0.82 |  |  |  | 3.28 |  |  |  | Not Started
70 | 2026-10-09 | Oct 2026 | Fri | 4 | 3.28 | 0.82 |  |  |  | 3.28 |  |  |  | Not Started
71 | 2026-10-10 | Oct 2026 | Sat | 4 | 3.28 | 0.82 |  |  |  | 3.28 |  |  |  | Not Started
72 | 2026-10-11 | Oct 2026 | Sun | 4 | 3.28 | 0.82 |  |  |  | 3.28 |  |  |  | Not Started
73 | 2026-10-12 | Oct 2026 | Mon | 4 | 3.28 | 0.82 |  |  |  | 3.28 |  |  |  | Not Started
74 | 2026-10-13 | Oct 2026 | Tue | 4 | 3.28 | 0.82 |  |  |  | 3.28 |  |  |  | Not Started
75 | 2026-10-14 | Oct 2026 | Wed | 4 | 3.28 | 0.82 |  |  |  | 3.28 |  |  |  | Not Started
76 | 2026-10-15 | Oct 2026 | Thu | 4 | 3.28 | 0.82 |  |  |  | 3.28 |  |  |  | Not Started
77 | 2026-10-16 | Oct 2026 | Fri | 4 | 3.28 | 0.82 |  |  |  | 3.28 |  |  |  | Not Started
78 | 2026-10-17 | Oct 2026 | Sat | 4 | 3.28 | 0.82 |  |  |  | 3.28 |  |  |  | Not Started
79 | 2026-10-18 | Oct 2026 | Sun | 4 | 3.28 | 0.82 |  |  |  | 3.28 |  |  |  | Not Started
80 | 2026-10-19 | Oct 2026 | Mon | 4 | 3.28 | 0.82 |  |  |  | 3.28 |  |  |  | Not Started
81 | 2026-10-20 | Oct 2026 | Tue | 4 | 3.28 | 0.82 |  |  |  | 3.28 |  |  |  | Not Started
82 | 2026-10-21 | Oct 2026 | Wed | 4 | 3.28 | 0.82 |  |  |  | 3.28 |  |  |  | Not Started
83 | 2026-10-22 | Oct 2026 | Thu | 4 | 3.28 | 0.82 |  |  |  | 3.28 |  |  |  | Not Started
84 | 2026-10-23 | Oct 2026 | Fri | 4 | 3.28 | 0.82 |  |  |  | 3.28 |  |  |  | Not Started
85 | 2026-10-24 | Oct 2026 | Sat | 4 | 3.28 | 0.82 |  |  |  | 3.28 |  |  |  | Not Started
86 | 2026-10-25 | Oct 2026 | Sun | 4 | 3.28 | 0.82 |  |  |  | 3.28 |  |  |  | Not Started
87 | 2026-10-26 | Oct 2026 | Mon | 4 | 3.28 | 0.82 |  |  |  | 3.28 |  |  |  | Not Started
88 | 2026-10-27 | Oct 2026 | Tue | 4 | 3.28 | 0.82 |  |  |  | 3.28 |  |  |  | Not Started
89 | 2026-10-28 | Oct 2026 | Wed | 4 | 3.28 | 0.82 |  |  |  | 3.28 |  |  |  | Not Started
90 | 2026-10-29 | Oct 2026 | Thu | 4 | 3.28 | 0.82 |  |  |  | 3.28 |  |  |  | Not Started
91 | 2026-10-30 | Oct 2026 | Fri | 4 | 3.28 | 0.82 |  |  |  | 3.28 |  |  |  | Not Started
92 | 2026-10-31 | Oct 2026 | Sat | 4 | 3.28 | 0.82 |  |  |  | 3.28 |  |  |  | Not Started
93 | 2026-11-01 | Nov 2026 | Sun | 4 | 3.28 | 0.82 |  |  |  | 3.28 |  |  |  | Not Started
94 | 2026-11-02 | Nov 2026 | Mon | 4 | 3.28 | 0.82 |  |  |  | 3.28 |  |  |  | Not Started
95 | 2026-11-03 | Nov 2026 | Tue | 4 | 3.28 | 0.82 |  |  |  | 3.28 |  |  |  | Not Started
96 | 2026-11-04 | Nov 2026 | Wed | 4 | 3.28 | 0.82 |  |  |  | 3.28 |  |  |  | Not Started
97 | 2026-11-05 | Nov 2026 | Thu | 4 | 3.28 | 0.82 |  |  |  | 3.28 |  |  |  | Not Started
98 | 2026-11-06 | Nov 2026 | Fri | 4 | 3.28 | 0.82 |  |  |  | 3.28 |  |  |  | Not Started
99 | 2026-11-07 | Nov 2026 | Sat | 4 | 3.28 | 0.82 |  |  |  | 3.28 |  |  |  | Not Started
100 | 2026-11-08 | Nov 2026 | Sun | 4 | 3.28 | 0.82 |  |  |  | 3.28 |  |  |  | Not Started
101 | 2026-11-09 | Nov 2026 | Mon | 4 | 3.28 | 0.82 |  |  |  | 3.28 |  |  |  | Not Started
102 | 2026-11-10 | Nov 2026 | Tue | 4 | 3.28 | 0.82 |  |  |  | 3.28 |  |  |  | Not Started
103 | 2026-11-11 | Nov 2026 | Wed | 4 | 3.28 | 0.82 |  |  |  | 3.28 |  |  |  | Not Started
104 | 2026-11-12 | Nov 2026 | Thu | 4 | 3.28 | 0.82 |  |  |  | 3.28 |  |  |  | Not Started
105 | 2026-11-13 | Nov 2026 | Fri | 4 | 3.28 | 0.82 |  |  |  | 3.28 |  |  |  | Not Started
106 | 2026-11-14 | Nov 2026 | Sat | 4 | 3.28 | 0.82 |  |  |  | 3.28 |  |  |  | Not Started
107 | 2026-11-15 | Nov 2026 | Sun | 4 | 3.27 | 0.82 |  |  |  | 3.27 |  |  |  | Not Started
108 | 2026-11-16 | Nov 2026 | Mon | 4 | 3.27 | 0.82 |  |  |  | 3.27 |  |  |  | Not Started
109 | 2026-11-17 | Nov 2026 | Tue | 4 | 3.27 | 0.82 |  |  |  | 3.27 |  |  |  | Not Started
110 | 2026-11-18 | Nov 2026 | Wed | 4 | 3.27 | 0.82 |  |  |  | 3.27 |  |  |  | Not Started
111 | 2026-11-19 | Nov 2026 | Thu | 4 | 3.27 | 0.82 |  |  |  | 3.27 |  |  |  | Not Started
112 | 2026-11-20 | Nov 2026 | Fri | 4 | 3.27 | 0.82 |  |  |  | 3.27 |  |  |  | Not Started
113 | 2026-11-21 | Nov 2026 | Sat | 4 | 3.27 | 0.82 |  |  |  | 3.27 |  |  |  | Not Started
114 | 2026-11-22 | Nov 2026 | Sun | 4 | 3.27 | 0.82 |  |  |  | 3.27 |  |  |  | Not Started
115 | 2026-11-23 | Nov 2026 | Mon | 4 | 3.27 | 0.82 |  |  |  | 3.27 |  |  |  | Not Started
116 | 2026-11-24 | Nov 2026 | Tue | 4 | 3.27 | 0.82 |  |  |  | 3.27 |  |  |  | Not Started
117 | 2026-11-25 | Nov 2026 | Wed | 4 | 3.27 | 0.82 |  |  |  | 3.27 |  |  |  | Not Started
118 | 2026-11-26 | Nov 2026 | Thu | 4 | 3.27 | 0.82 |  |  |  | 3.27 |  |  |  | Not Started
119 | 2026-11-27 | Nov 2026 | Fri | 4 | 3.27 | 0.82 |  |  |  | 3.27 |  |  |  | Not Started
120 | 2026-11-28 | Nov 2026 | Sat | 4 | 3.27 | 0.82 |  |  |  | 3.27 |  |  |  | Not Started
121 | 2026-11-29 | Nov 2026 | Sun | 4 | 3.27 | 0.82 |  |  |  | 3.27 |  |  |  | Not Started
122 | 2026-11-30 | Nov 2026 | Mon | 4 | 3.27 | 0.82 |  |  |  | 3.27 |  |  |  | Not Started

## Monthly Summary
Month | Planned Hours | Actual Hours | Variance | Completion Rate
Aug 2026 | 101.68 | 0
Sep 2026 | 98.4 | 0
Oct 2026 | 101.68 | 0
Nov 2026 | 98.24 | 0

## Phases & Risks
Delivery Phases & Risk Register
Phase | Objective
Mobilization | Confirm inputs, guidelines, access, and team readiness.
Pilot | Validate instructions and calibrate quality expectations.
Production | Deliver the planned workload against daily targets.
Closeout | Resolve remaining issues and confirm final acceptance.
Risk | Impact | Mitigation
Late or incomplete source data | Reduces available production time. | Confirm readiness and escalation owners before kickoff.
Guideline ambiguity | Creates rework and inconsistent quality. | Run a pilot and document adjudicated examples.
Team availability | Daily targets may be missed. | Track attendance and rebalance work weekly.

## Assumptions
Planning Assumptions
No. | Assumption
1 | Input data and annotation guidelines are available before kickoff.
2 | All four annotators complete onboarding before production begins.
3 | Quality review occurs throughout delivery rather than only at the end.
4 | Calendar days scheduling was used.
5 | Total target hours are distributed across 122 scheduled days.